## کنترل قرارداد
خلاصه مالی خرید عایق گرم و سرد و آلومینیوم | [8 empty] | شماره قرارداد: ADSH-P-PO-GE-098
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [8 empty] | تاریخ قرارداد: 1401/04/22
فروشنده: شرکت جهان عایق پارس | [8 empty] | تاریخ تهیه گزارش: 1401/06/28
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (یورو) | مبلغ قرارداد (یورو) | مقادیر رسید شده | درصد کالای دریافتی | مبلغ کل (یورو) | فاکتور
1 | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 277.5 | 1.077 | 298.8675 | 0 | 0% | 0 | 36 | 36 | 38.772
2 | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 22 | 1.508 | 33.176 | 22 | 100% | 33.176 | 4 | -18 | 6.032
3 | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.297 | 3.4455 | 1.5 | 100% | 3.4455 | 112 | 110.5 | 257.264
4 | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1558 | 1.149 | 1790.142 | 1558 | 100% | 1790.142 | 30 | -1528 | 34.47
5 | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 122.5 | 1.723 | 211.0675 | 122.5 | 100% | 211.0675 | 54 | -68.5 | 93.042
6 | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 4.5 | 2.44 | 10.98 | 4.5 | 100% | 10.98 | 14 | 9.5 | 34.16
7 | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1104.5 | 1.192 | 1316.564 | 0 | 0% | 0 | 10 | 10 | 11.92
8 | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 323.5 | 1.795 | 580.6825 | 0 | 0% | 0 | 6 | 6 | 10.77
9 | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 3.5 | 2.656 | 9.296 | 3.5 | 100% | 9.296 | 12 | 8.5 | 31.872
10 | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1697.5 | 1.508 | 2559.83 | 0 | 0% | 0 | 10 | 10 | 15.08
11 | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 131 | 2.104 | 275.624 | 0 | 0% | 0 | 10 | 10 | 21.04
12 | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.943 | 4.4145 | 0 | 0% | 0 |  | 0 | 0
13 | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 2009 | 1.579 | 3172.211 | 110 | 5.475% | 173.69 | 3 | -107 | 4.737
14 | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 956 | 2.44 | 2332.64 | 0 | 0% | 0 | 8 | 8 | 19.52
15 | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 37.5 | 3.302 | 123.825 | 37.5 | 100% | 123.825 | 2 | -35.5 | 6.604
16 | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 4.235 | 6.3525 | 0 | 0% | 0 | 4 | 4 | 16.94
17 | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1170.5 | 2.154 | 2521.257 | 575 | 49.12% | 1238.55 | 53 | -522 | 114.162
18 | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 620.5 | 3.086 | 1914.863 | 620.5 | 100% | 1914.863 | 6 | -614.5 | 18.516
19 | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 139 | 4.074 | 566.286 | 0 | 0% | 0 | 4 | 4 | 16.296
20 | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 76 | 2.496 | 189.696 | 0 | 0% | 0 | 465 | 465 | 1160.64
21 | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1020 | 3.589 | 3660.78 | 0 | 0% | 0 | 97 | 97 | 348.133
22 | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 133.5 | 4.737 | 632.3895 | 0 | 0% | 0 | 12 | 12 | 56.844
23 | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 68.5 | 5.956 | 407.986 | 0 | 0% | 0 | 3 | 3 | 17.868
24 | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 132 | 3.484 | 459.888 | 132 | 100% | 459.888
25 | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1479.5 | 4.88 | 7219.96 | 0 | 0% | 0
26 | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 48.5 | 6.315 | 306.2775 | 48.5 | 100% | 306.2775
27 | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 371 | 7.822 | 2901.962 | 371 | 100% | 2901.962
28 | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 440 | 9.832 | 4326.08 | 430 | 97.73% | 4227.76
29 | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 128 | 6.315 | 808.32 | 0 | 0% | 0
30 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 132 | 15.892 | 2097.744 | 0 | 0% | 0
31 | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 10 | 4.339 | 43.39 | 0 | 0% | 0
32 | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 178.5 | 7.751 | 1383.5535 | 84 | 47.06% | 651.084
33 | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 348 | 9.472 | 3296.256 | 0 | 0% | 0
34 | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 238 | 11.553 | 2749.614 | 0 | 0% | 0
35 | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 187 | 7.751 | 1449.437 | 0 | 0% | 0
36 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 223 | 15.892 | 3543.916 | 0 | 0% | 0
37 | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 40 | 5.134 | 205.36 | 0 | 0% | 0
38 | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 102.5 | 9.329 | 956.2225 | 0 | 0% | 0
39 | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 573.5 | 11.267 | 6461.6245 | 0 | 0% | 0
40 | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 216 | 13.634 | 2944.944 | 216 | 100% | 2944.944
41 | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 241 | 9.329 | 2248.289 | 0 | 0% | 0
42 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 328 | 15.892 | 5212.576 | 0 | 0% | 0
43 | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 177.5 | 9.329 | 1655.8975 | 0 | 0% | 0
44 |  | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 253 | 16.7 | 4225.1 | 0 | 0% | 0
45 | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | متر | 1.1 | 10.888 | 11.9768 | 0 | 0% | 0
46 | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 5.5 | 7.801 | 42.9055 | 0 | 0% | 0
47 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 87.78 | 15.892 | 1394.9998 | 0 | 0% | 0
48 | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1007.6 | 17.508 | 17641.0608 | 0 | 0% | 0
49 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1310.1 | 18.316 | 23995.7916 | 0 | 0% | 0
50 | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1243 | 19.124 | 23771.132 | 0 | 0% | 0
51 | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 403.7 | 19.932 | 8046.5484 | 0 | 0% | 0
52 | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 822.8 | 20.74 | 17064.872 | 0 | 0% | 0
53 | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 11.88 | 21.548 | 255.9902 | 0 | 0% | 0
54 | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 17.508 | 4025.0892 | 0 | 0% | 0
55 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 18.316 | 4210.8484 | 0 | 0% | 0
56 | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 5869.6 | 11.313 | 66402.7848 | 5869.6 | 100% | 66402.7848
57 | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 6906.9 | 15.084 | 104183.6796 | 6906.9 | 100% | 104183.6796
58 | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 2156 | 18.855 | 40651.38 | 2156 | 100% | 40651.38
59 | Insulation-Acc | Accessories for Insulation | ست | 1 |  | 0 | 0 | 0% | 0
60 | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | متر | 1.1 | 6.341 | 6.9751 | 0 | 0% | 0
61 | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | متر | 20.9 | 6.95 | 145.255 | 0 | 0% | 0
62 | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 8.8 | 9.627 | 84.7176 | 0 | 0% | 0
63 | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 1.1 | 14.464 | 15.9104 | 0 | 0% | 0
64 | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 2.2 | 12.024 | 26.4528 | 0 | 0% | 0
65 | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 908.6 | 11.092 | 10078.1912 | 0 | 0% | 0
66 | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 193.6 | 14.626 | 2831.5936 | 0 | 0% | 0
67 | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 85.8 | 21.123 | 1812.3534 | 0 | 0% | 0
68 | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 34.1 | 25.184 | 858.7744 | 0 | 0% | 0
69 | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 38.5 | 33.513 | 1290.2505 | 0 | 0% | 0
70 | 4YYYYYE06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 125.4 | 56.052 | 7028.9208 | 0 | 0% | 0
71 | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 39.6 | 44.68 | 1769.328 | 0 | 0% | 0
72 | ACCESSORY | تسمه استنلس استیل سایز 13mm*0/5mm | متر | 43500 | 0.61 | 26535 | 43500 | 100% | 26535
73 | ACCESSORY | تسمه استنلس استیل سایز 19mm*0/5mm | متر | 13000 | 1 | 13000 | 13000 | 100% | 13000
74 | ACCESSORY | بست استنلس استیل سایز 13mm*0/5mm | عدد | 72000 | 0.08 | 5760 | 72000 | 100% | 5760
75 | ACCESSORY | بست استنلس استیل سایز 19mm*0/5mm | عدد | 3500 | 0.08 | 280 | 3500 | 100% | 280
76 | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 | عدد | 120000 | 0.066 | 7920 | 120000 | 100% | 7920
77 | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 | عدد | 80000 | 0.057 | 4560 | 80000 | 100% | 4560
78 | ACCESSORY | واشر لئوپرن | عدد | 120000 | 0.036 | 4320 | 53100 | 44.25% | 1911.6
79 | ACCESSORY | ماستیک METAL SEALANT | عدد | 3090 | 6.6 | 20394 | 0 | 0% | 0
80 | ACCESSORY | کلیپس S | عدد | 3200 | 0.09 | 288 | 3200 | 100% | 288
81 | ACCESSORY | سیم استنلس استیل به قطر 1mm | متر | 106000 | 0.21 | 22260 | 106000 | 100% | 22260
82 | ACCESSORY | نوارچسب نخ دار تقویت شده فیلامنت با عرض 50 میلیمتر | حلقه | 75 | 15.95 | 1196.25 | 75 | 100% | 1196.25
83 | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | کیلوگرم | 2075 | 2.65 | 5498.75 | 2075 | 100% | 5498.75
84 | ACCESSORY | Joint Sealant Mastic JAP 81-84 | کیلوگرم | 550 | 3 | 1650 | 550 | 100% | 1650
85 | ACCESSORY | Glass Cloth Mesh | کیلوگرم | 750 | 1.3 | 975 | 750 | 100% | 975
[6 empty] | 529403.5689 |  |  | 320073.3949
خلاصه محاسبات پرداخت صورت حساب: | [5 empty] | (یورو) | توضیحات:
جمع کالای دریافتی | [5 empty] | 320073.3949 | کالاهای رسید شده با شماره مرجع MRS--JAY-098-001 الی MRS-JAY-098-009 در این مرحله صورتحساب شده است که تماما در بازه مجاز قرارداد به انبار رسید شده است لذا مشمول جریمه تاخیر نمی باشد.
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 28806.6055
جمع صورتحسابها | [5 empty] | 348880.0004
کسور:
استهلاک پیش پرداخت (30%) | [5 empty] | 96022.0185
جمع کسور | [5 empty] | 96022.0185
خالص قابل پرداخت | [5 empty] | 252857.982

## کنترل قرارداد (2)
خلاصه مالی خرید عایق گرم و سرد و آلومینیوم | [10 empty] | شماره قرارداد: ADSH-P-PO-GE-098
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [10 empty] | تاریخ قرارداد: 1401/04/22
فروشنده: شرکت جهان عایق پارس | [10 empty] | تاریخ تهیه گزارش: 1401/07/21
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (یورو) | مبلغ قرارداد (یورو) | مقادیر رسید شده مرحله اول | مقادیر رسید شده مرحله دوم | جمع مقادیر رسید شده | درصد کالای دریافتی | مبلغ کالای دریافتی (یورو) | فاکتور
1 | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 277.5 | 1.077 | 298.8675 | 0 | 0 | 0 | 0% | 0 | 36 | 36 | 38.772
2 | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 22 | 1.508 | 33.176 | 22 | 0 | 22 | 100% | 33.176 | 4 | -18 | 6.032
3 | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.297 | 3.4455 | 1.5 | 0 | 1.5 | 100% | 3.4455 | 112 | 110.5 | 257.264
4 | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1558 | 1.149 | 1790.142 | 1558 | 0 | 1558 | 100% | 1790.142 | 30 | -1528 | 34.47
5 | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 122.5 | 1.723 | 211.0675 | 122.5 | 0 | 122.5 | 100% | 211.0675 | 54 | -68.5 | 93.042
6 | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 4.5 | 2.44 | 10.98 | 4.5 | 0 | 4.5 | 100% | 10.98 | 14 | 9.5 | 34.16
7 | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1104.5 | 1.192 | 1316.564 | 0 | 0 | 0 | 0% | 0 | 10 | 10 | 11.92
8 | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 323.5 | 1.795 | 580.6825 | 0 | 0 | 0 | 0% | 0 | 6 | 6 | 10.77
9 | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 3.5 | 2.656 | 9.296 | 3.5 | 0 | 3.5 | 100% | 9.296 | 12 | 8.5 | 31.872
10 | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1697.5 | 1.508 | 2559.83 | 0 | 0 | 0 | 0% | 0 | 10 | 10 | 15.08
11 | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 131 | 2.104 | 275.624 | 0 | 0 | 0 | 0% | 0 | 10 | 10 | 21.04
12 | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.943 | 4.4145 | 0 | 0 | 0 | 0% | 0 |  | 0 | 0
13 | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 2009 | 1.579 | 3172.211 | 110 | 0 | 110 | 5.475% | 173.69 | 3 | -107 | 4.737
14 | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 956 | 2.44 | 2332.64 | 0 | 0 | 0 | 0% | 0 | 8 | 8 | 19.52
15 | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 37.5 | 3.302 | 123.825 | 37.5 | 0 | 37.5 | 100% | 123.825 | 2 | -35.5 | 6.604
16 | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 4.235 | 6.3525 | 0 | 0 | 0 | 0% | 0 | 4 | 4 | 16.94
17 | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1170.5 | 2.154 | 2521.257 | 575 | 0 | 575 | 49.12% | 1238.55 | 53 | -522 | 114.162
18 | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 620.5 | 3.086 | 1914.863 | 620.5 | 0 | 620.5 | 100% | 1914.863 | 6 | -614.5 | 18.516
19 | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 139 | 4.074 | 566.286 | 0 | 139 | 139 | 100% | 566.286 | 4 | 4 | 16.296
20 | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 76 | 2.496 | 189.696 | 0 | 0 | 0 | 0% | 0 | 465 | 465 | 1160.64
21 | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1020 | 3.589 | 3660.78 | 0 | 0 | 0 | 0% | 0 | 97 | 97 | 348.133
22 | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 133.5 | 4.737 | 632.3895 | 0 | 0 | 0 | 0% | 0 | 12 | 12 | 56.844
23 | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 68.5 | 5.956 | 407.986 | 0 | 0 | 0 | 0% | 0 | 3 | 3 | 17.868
24 | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 132 | 3.484 | 459.888 | 132 | 0 | 132 | 100% | 459.888
25 | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1479.5 | 4.88 | 7219.96 | 0 | 0 | 0 | 0% | 0
26 | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 48.5 | 6.315 | 306.2775 | 48.5 | 0 | 48.5 | 100% | 306.2775
27 | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 371 | 7.822 | 2901.962 | 371 | 0 | 371 | 100% | 2901.962
28 | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 440 | 9.832 | 4326.08 | 430 | 0 | 430 | 97.73% | 4227.76
29 | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 128 | 6.315 | 808.32 | 0 | 0 | 0 | 0% | 0
30 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 132 | 15.892 | 2097.744 | 0 | 132 | 132 | 100% | 2097.744
31 | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 10 | 4.339 | 43.39 | 0 | 0 | 0 | 0% | 0
32 | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 178.5 | 7.751 | 1383.5535 | 84 | 0 | 84 | 47.06% | 651.084
33 | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 348 | 9.472 | 3296.256 | 0 | 0 | 0 | 0% | 0
34 | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 238 | 11.553 | 2749.614 | 0 | 0 | 0 | 0% | 0
35 | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 187 | 7.751 | 1449.437 | 0 | 0 | 0 | 0% | 0
36 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 223 | 15.892 | 3543.916 | 0 | 223 | 223 | 100% | 3543.916
37 | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 40 | 5.134 | 205.36 | 0 | 0 | 0 | 0% | 0
38 | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 102.5 | 9.329 | 956.2225 | 0 | 0 | 0 | 0% | 0
39 | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 573.5 | 11.267 | 6461.6245 | 0 | 155 | 155 | 27.03% | 1746.385
40 | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 216 | 13.634 | 2944.944 | 216 | 0 | 216 | 100% | 2944.944
41 | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 241 | 9.329 | 2248.289 | 0 | 0 | 0 | 0% | 0
42 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 328 | 15.892 | 5212.576 | 0 | 328 | 328 | 100% | 5212.576
43 | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 177.5 | 9.329 | 1655.8975 | 0 | 0 | 0 | 0% | 0
44 | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 253 | 16.7 | 4225.1 | 0 | 253 | 253 | 100% | 4225.1
45 | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | متر | 1.1 | 10.888 | 11.9768 | 0 | 1.1 | 1.1 | 100% | 11.9768
46 | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 5.5 | 7.801 | 42.9055 | 0 | 5.5 | 5.5 | 100% | 42.9055
47 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 87.78 | 15.892 | 1394.9998 | 0 | 87.78 | 87.78 | 100% | 1394.9998
48 | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1007.6 | 17.508 | 17641.0608 | 0 | 1237.5 | 1237.5 | 122.8% | 21666.15
49 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1310.1 | 18.316 | 23995.7916 | 0 | 1310.1 | 1310.1 | 100% | 23995.7916
50 | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1243 | 19.124 | 23771.132 | 0 | 1243 | 1243 | 100% | 23771.132
51 | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 403.7 | 19.932 | 8046.5484 | 0 | 403.7 | 403.7 | 100% | 8046.5484
52 | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 822.8 | 20.74 | 17064.872 | 0 | 822.8 | 822.8 | 100% | 17064.872
53 | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 11.88 | 21.548 | 255.9902 | 0 | 11.88 | 11.88 | 100% | 255.9902
54 | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 17.508 | 4025.0892 | 0 | 0 | 0 | 0% | 0
55 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 18.316 | 4210.8484 | 0 | 229.9 | 229.9 | 100% | 4210.8484
56 | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 5869.6 | 11.313 | 66402.7848 | 5869.601 | 0 | 5869.601 | 100% | 66402.7961
57 | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 6906.9 | 15.084 | 104183.6796 | 6906.9 | 0 | 6906.9 | 100% | 104183.6796
58 | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 2156 | 18.855 | 40651.38 | 2156 | 0 | 2156 | 100% | 40651.38
59 | Insulation-Acc | Accessories for Insulation | ست | 1 |  | 0 | 0 | 0 | 0 | 0% | 0
60 | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | متر | 1.1 | 6.341 | 6.9751 | 0 | 1.1 | 1.1 | 100% | 6.9751
61 | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | متر | 20.9 | 6.95 | 145.255 | 0 | 20.9 | 20.9 | 100% | 145.255
62 | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 8.8 | 9.627 | 84.7176 | 0 | 8.8 | 8.8 | 100% | 84.7176
63 | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 1.1 | 14.464 | 15.9104 | 0 | 1.1 | 1.1 | 100% | 15.9104
64 | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 2.2 | 12.024 | 26.4528 | 0 | 2.2 | 2.2 | 100% | 26.4528
65 | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 908.6 | 11.092 | 10078.1912 | 0 | 908.6 | 908.6 | 100% | 10078.1912
66 | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 193.6 | 14.626 | 2831.5936 | 0 | 193.6 | 193.6 | 100% | 2831.5936
67 | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 85.8 | 21.123 | 1812.3534 | 0 | 85.8 | 85.8 | 100% | 1812.3534
68 | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 34.1 | 25.184 | 858.7744 | 0 | 34.1 | 34.1 | 100% | 858.7744
69 | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 38.5 | 33.513 | 1290.2505 | 0 | 38.5 | 38.5 | 100% | 1290.2505
70 | 4YYYYYG06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 125.4 | 56.052 | 7028.9208 | 0 | 125.4 | 125.4 | 100% | 7028.9208
71 | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 39.6 | 44.68 | 1769.328 | 0 | 39.6 | 39.6 | 100% | 1769.328
72 | ACCESSORY | تسمه استنلس استیل سایز 13mm*0/5mm | متر | 43500 | 0.61 | 26535 | 43500 | 0 | 43500 | 100% | 26535
73 | ACCESSORY | تسمه استنلس استیل سایز 19mm*0/5mm | متر | 13000 | 1 | 13000 | 13000 | 0 | 13000 | 100% | 13000
74 | ACCESSORY | بست استنلس استیل سایز 13mm*0/5mm | عدد | 72000 | 0.08 | 5760 | 72000 | 0 | 72000 | 100% | 5760
75 | ACCESSORY | بست استنلس استیل سایز 19mm*0/5mm | عدد | 3500 | 0.08 | 280 | 3500 | 0 | 3500 | 100% | 280
76 | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 | عدد | 120000 | 0.066 | 7920 | 120000 | 0 | 120000 | 100% | 7920
77 | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 | عدد | 80000 | 0.057 | 4560 | 80000 | 0 | 80000 | 100% | 4560
78 | ACCESSORY | واشر لئوپرن | عدد | 120000 | 0.036 | 4320 | 53100 | 0 | 53100 | 44.25% | 1911.6
79 | ACCESSORY | ماستیک METAL SEALANT | عدد | 3090 | 6.6 | 20394 | 0 | 0 | 0 | 0% | 0
80 | ACCESSORY | کلیپس S | عدد | 3200 | 0.09 | 288 | 3200 | 0 | 3200 | 100% | 288
81 | ACCESSORY | سیم استنلس استیل به قطر 1mm | متر | 106000 | 0.21 | 22260 | 106000 | 0 | 106000 | 100% | 22260
82 | ACCESSORY | نوارچسب نخ دار تقویت شده فیلامنت با عرض 50 میلیمتر | حلقه | 75 | 15.95 | 1196.25 | 75 | 0 | 75 | 100% | 1196.25
83 | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | کیلوگرم | 2075 | 2.65 | 5498.75 | 2075 | 0 | 2075 | 100% | 5498.75
84 | ACCESSORY | Joint Sealant Mastic JAP 81-84 | کیلوگرم | 550 | 3 | 1650 | 550 | 0 | 550 | 100% | 1650
85 | ACCESSORY | Glass Cloth Mesh | کیلوگرم | 750 | 1.3 | 975 | 750 | 0 | 750 | 100% | 975
[6 empty] | 529403.5689 |  |  |  |  | 463875.3507
خلاصه محاسبات پرداخت صورت حساب: | [5 empty] | (یورو) | توضیحات:
جمع کالای دریافتی | [5 empty] | 463875.3507 | صورتحسابهای مرحله اول: MRS-JAY-098-009 الی MRS-JAY-098-001 صورتحسابهای مرحله دوم: MRS-JAY-098-018 الی MRS-JAY-098-010 تاریخ انعقاد قرارداد: 1401/04/22 تاریخ شروع قرارداد برابر با تاریخ ابلاغ قرارداد: 1401/04/26 تاریخ پیش پرداخت: 1401/05/09 مدت قرارداد: 60 روز تقویمی پیش از شروع قرارداد (تاخیر در پرداخت پیش پرداخت به مدت زمان تحویل اضافه می شود) سر رسید تاریخ تحویل (با توجه به توضیحات فوق): 1401/07/07 با توجه به استعلام اخذ شده از واحد برنامه ریزی، تاخیر در ارسال پارت دوم با هماهنگی خریدار و تحویل طی بازه های اعلامی توسط خریدار بوده است.
کسر می شود: کالای صورتحساب شده طی مراحل قبلی | [5 empty] | 320073.3949
جمع کالای دریافتی طی مرحله دوم | [5 empty] | 143801.9558
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 12942.18 | [8 empty] | 12942.176 | 12942.18 | 0.0039768
جمع صورتحسابهای مرحله دوم | [5 empty] | 156744.1358
کسور:
استهلاک پیش پرداخت (30%) | [5 empty] | 43140.5867
جمع کسور | [5 empty] | 43140.5867
خالص قابل پرداخت | [5 empty] | 113603.5491

## کنترل قرارداد (3)
خلاصه مالی خرید عایق گرم و سرد و آلومینیوم | [12 empty] | شماره قرارداد: ADSH-P-PO-GE-098
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [12 empty] | تاریخ قرارداد: 1401/04/22
فروشنده: شرکت جهان عایق پارس | [12 empty] | تاریخ تهیه گزارش: 1401/11/17
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (یورو) | مبلغ قرارداد (یورو) | مقادیر رسید شده مرحله اول | مقادیر رسید شده مرحله دوم | مقادیر رسید شده مرحله سوم | مقادیر رسید شده مرحله چهارم | جمع مقادیر رسید شده | درصد کالای دریافتی | مبلغ کالای دریافتی (یورو) | فاکتور
1 | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 277.5 | 1.077 | 298.8675 | 0 | 0 | 0 | 277.5 | 277.5 | 100% | 298.8675 | 36 | 36 | 38.772
2 | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 22 | 1.508 | 33.176 | 22 | 0 | 0 | 0 | 22 | 100% | 33.176 | 4 | -18 | 6.032
3 | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.297 | 3.4455 | 1.5 | 0 | 0 | 0 | 1.5 | 100% | 3.4455 | 112 | 110.5 | 257.264
4 | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1558 | 1.149 | 1790.142 | 1558 | 0 | 0 | 0 | 1558 | 100% | 1790.142 | 30 | -1528 | 34.47
5 | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 122.5 | 1.723 | 211.0675 | 122.5 | 0 | 0 | 0 | 122.5 | 100% | 211.0675 | 54 | -68.5 | 93.042
6 | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 4.5 | 2.44 | 10.98 | 4.5 | 0 | 0 | 0 | 4.5 | 100% | 10.98 | 14 | 9.5 | 34.16
7 | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1104.5 | 1.192 | 1316.564 | 0 | 0 | 1104.5 | 0 | 1104.5 | 100% | 1316.564 | 10 | 10 | 11.92
8 | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 323.5 | 1.795 | 580.6825 | 0 | 0 | 0 | 323.5 | 323.5 | 100% | 580.6825 | 6 | 6 | 10.77
9 | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 3.5 | 2.656 | 9.296 | 3.5 | 0 | 0 | 0 | 3.5 | 100% | 9.296 | 12 | 8.5 | 31.872
10 | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1697.5 | 1.508 | 2559.83 | 0 | 0 | 0 | 1697.5 | 1697.5 | 100% | 2559.83 | 10 | 10 | 15.08
11 | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 131 | 2.104 | 275.624 | 0 | 0 | 131 | 0 | 131 | 100% | 275.624 | 10 | 10 | 21.04
12 | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.943 | 4.4145 | 0 | 0 | 0 | 1.5 | 1.5 | 100% | 4.4145 |  | 0 | 0
13 | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 2009 | 1.579 | 3172.211 | 110 | 0 | 1782 | 117 | 2009 | 100% | 3172.211 | 3 | -107 | 4.737
14 | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 956 | 2.44 | 2332.64 | 0 | 0 | 636 | 320 | 956 | 100% | 2332.64 | 8 | 8 | 19.52
15 | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 37.5 | 3.302 | 123.825 | 37.5 | 0 | 0 | 0 | 37.5 | 100% | 123.825 | 2 | -35.5 | 6.604
16 | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 4.235 | 6.3525 | 0 | 0 | 0 | 1.5 | 1.5 | 100% | 6.3525 | 4 | 4 | 16.94
17 | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1170.5 | 2.154 | 2521.257 | 575 | 0 | 96 | 499.5 | 1170.5 | 100% | 2521.257 | 53 | -522 | 114.162
18 | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 620.5 | 3.086 | 1914.863 | 620.5 | 0 | 0 | 0 | 620.5 | 100% | 1914.863 | 6 | -614.5 | 18.516
19 | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 139 | 4.074 | 566.286 | 0 | 139 | 0 | 0 | 139 | 100% | 566.286 | 4 | 4 | 16.296
20 | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 76 | 2.496 | 189.696 | 0 | 0 | 76 | 0 | 76 | 100% | 189.696 | 465 | 465 | 1160.64
21 | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1020 | 3.589 | 3660.78 | 0 | 0 | 921 | 99 | 1020 | 100% | 3660.78 | 97 | 97 | 348.133
22 | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 133.5 | 4.737 | 632.3895 | 0 | 0 | 45 | 88.5 | 133.5 | 100% | 632.3895 | 12 | 12 | 56.844
23 | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 68.5 | 5.956 | 407.986 | 0 | 0 | 0 | 68.5 | 68.5 | 100% | 407.986 | 3 | 3 | 17.868
24 | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 132 | 3.484 | 459.888 | 132 | 0 | 0 | 0 | 132 | 100% | 459.888
25 | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1479.5 | 4.88 | 7219.96 | 0 | 0 | 0 | 1479.5 | 1479.5 | 100% | 7219.96
26 | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 48.5 | 6.315 | 306.2775 | 48.5 | 0 | 0 | 0 | 48.5 | 100% | 306.2775
27 | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 371 | 7.822 | 2901.962 | 371 | 0 | 0 | 0 | 371 | 100% | 2901.962
28 | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 440 | 9.832 | 4326.08 | 430 | 0 | 0 | 10 | 440 | 100% | 4326.08
29 | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 128 | 6.315 | 808.32 | 0 | 0 | 128 | 0 | 128 | 100% | 808.32
30 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 132 | 15.892 | 2097.744 | 0 | 132 | 0 | 579 | 711 | 538.6% | 11299.212
31 | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 10 | 4.339 | 43.39 | 0 | 0 | 10 | 0 | 10 | 100% | 43.39
32 | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 178.5 | 7.751 | 1383.5535 | 40 | 0 | 138.5 | 0 | 178.5 | 100% | 1383.5535
33 | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 348 | 9.472 | 3296.256 | 0 | 0 | 0 | 348 | 348 | 100% | 3296.256
34 | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 238 | 11.553 | 2749.614 | 0 | 0 | 0 | 238 | 238 | 100% | 2749.614
35 | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 187 | 7.751 | 1449.437 | 44 | 0 | 0 | 143 | 187 | 100% | 1449.437
36 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 223 | 15.892 | 3543.916 | 0 | 223 | 0 | 0 | 223 | 100% | 3543.916
37 | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 40 | 5.134 | 205.36 | 0 | 0 | 0 | 40 | 40 | 100% | 205.36
38 | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 102.5 | 9.329 | 956.2225 | 0 | 0 | 0 | 102.5 | 102.5 | 100% | 956.2225
39 | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 573.5 | 11.267 | 6461.6245 | 0 | 155 | 0 | 418.5 | 573.5 | 100% | 6461.6245
40 | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 216 | 13.634 | 2944.944 | 216 | 0 | 0 | 0 | 216 | 100% | 2944.944
41 | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 241 | 9.329 | 2248.289 | 0 | 0 | 0 | 241 | 241 | 100% | 2248.289
42 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 328 | 15.892 | 5212.576 | 0 | 328 | 0 | 24 | 352 | 107.3% | 5593.984
43 | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 177.5 | 9.329 | 1655.8975 | 0 | 0 | 0 | 0 | 177.5 | 100% | 1655.8975
44 | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 253 | 16.7 | 4225.1 | 0 | 253 | 0 | 0 | 253 | 100% | 4225.1
45 | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | متر | 1.1 | 10.888 | 11.9768 | 0 | 1.1 | 0 | 0 | 1.1 | 100% | 11.9768
46 | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 5.5 | 7.801 | 42.9055 | 0 | 5.5 | 0 | 0 | 5.5 | 100% | 42.9055
47 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 87.78 | 15.892 | 1394.9998 | 0 | 87.78 | 0 | 0 | 87.78 | 100% | 1394.9998
48 | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1007.6 | 17.508 | 17641.0608 | 0 | 1237.5 | 0 | 0 | 1237.5 | 122.8% | 21666.15
49 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1310.1 | 18.316 | 23995.7916 | 0 | 1310.1 | 0 | 153.6 | 1463.7 | 111.7% | 26809.1292
50 | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1243 | 19.124 | 23771.132 | 0 | 1243 | 0 | 0 | 1243 | 100% | 23771.132
51 | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 403.7 | 19.932 | 8046.5484 | 0 | 403.7 | 0 | 0 | 403.7 | 100% | 8046.5484
52 | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 822.8 | 20.74 | 17064.872 | 0 | 822.8 | 0 | 211 | 1033.8 | 125.6% | 21441.012
53 | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 11.88 | 21.548 | 255.9902 | 0 | 11.88 | 0 | 0 | 11.88 | 100% | 255.9902
54 | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 17.508 | 4025.0892 | 0 | 0 | 0 | 241.2 | 241.2 | 104.9% | 4222.9296
55 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 18.316 | 4210.8484 | 0 | 229.9 | 0 | 280.8 | 510.7 | 222.1% | 9353.9812
56 | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 5869.6 | 11.313 | 66402.7848 | 5869.601 | 0 | 0 | 0 | 5869.601 | 100% | 66402.7961
57 | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 6906.9 | 15.084 | 104183.6796 | 6906.9 | 0 | 0 | 0 | 6906.9 | 100% | 104183.6796
58 | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 2156 | 18.855 | 40651.38 | 2156 | 0 | 0 | 0 | 2156 | 100% | 40651.38
59 | Insulation-Acc | Accessories for Insulation | ست | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
60 | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | متر | 1.1 | 6.341 | 6.9751 | 0 | 1.1 | 0 | 0 | 1.1 | 100% | 6.9751
61 | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | متر | 20.9 | 6.95 | 145.255 | 0 | 20.9 | 0 | 0 | 20.9 | 100% | 145.255
62 | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 8.8 | 9.627 | 84.7176 | 0 | 8.8 | 0 | 0 | 8.8 | 100% | 84.7176
63 | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 1.1 | 14.464 | 15.9104 | 0 | 1.1 | 0 | 0 | 1.1 | 100% | 15.9104
64 | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 2.2 | 12.024 | 26.4528 | 0 | 2.2 | 0 | 0 | 2.2 | 100% | 26.4528
65 | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 908.6 | 11.092 | 10078.1912 | 0 | 908.6 | 0 | 0 | 908.6 | 100% | 10078.1912
66 | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 193.6 | 14.626 | 2831.5936 | 0 | 193.6 | 0 | 0 | 193.6 | 100% | 2831.5936
67 | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 85.8 | 21.123 | 1812.3534 | 0 | 85.8 | 0 | 0 | 85.8 | 100% | 1812.3534
68 | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 34.1 | 25.184 | 858.7744 | 0 | 34.1 | 0 | 0 | 34.1 | 100% | 858.7744
69 | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 38.5 | 33.513 | 1290.2505 | 0 | 38.5 | 0 | 0 | 38.5 | 100% | 1290.2505
70 | 4YYYYYG06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 125.4 | 56.052 | 7028.9208 | 0 | 125.4 | 0 | 0 | 125.4 | 100% | 7028.9208
71 | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 39.6 | 44.68 | 1769.328 | 0 | 39.6 | 0 | 0 | 39.6 | 100% | 1769.328
72 | ACCESSORY | تسمه استنلس استیل سایز 13mm*0/5mm | متر | 43500 | 0.61 | 26535 | 43500 | 0 | 0 | 0 | 43500 | 100% | 26535
73 | ACCESSORY | تسمه استنلس استیل سایز 19mm*0/5mm | متر | 13000 | 1 | 13000 | 13000 | 0 | 0 | 0 | 13000 | 100% | 13000
74 | ACCESSORY | بست استنلس استیل سایز 13mm*0/5mm | عدد | 72000 | 0.08 | 5760 | 72000 | 0 | 0 | 0 | 72000 | 100% | 5760
75 | ACCESSORY | بست استنلس استیل سایز 19mm*0/5mm | عدد | 3500 | 0.08 | 280 | 3500 | 0 | 0 | 0 | 3500 | 100% | 280
76 | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 | عدد | 120000 | 0.066 | 7920 | 120000 | 0 | 0 | 0 | 120000 | 100% | 7920
77 | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 | عدد | 80000 | 0.057 | 4560 | 80000 | 0 | 0 | 0 | 80000 | 100% | 4560
78 | ACCESSORY | واشر لئوپرن | عدد | 120000 | 0.036 | 4320 | 53100 | 0 | 66900 | 0 | 120000 | 100% | 4320
79 | ACCESSORY | ماستیک METAL SEALANT | عدد | 3090 | 6.6 | 20394 | 0 | 0 | 3090 | 750 | 3840 | 124.3% | 25344
80 | ACCESSORY | کلیپس S | عدد | 3200 | 0.09 | 288 | 3200 | 0 | 0 | 0 | 3200 | 100% | 288
81 | ACCESSORY | سیم استنلس استیل به قطر 1mm | متر | 106000 | 0.21 | 22260 | 106000 | 0 | 0 | 0 | 106000 | 100% | 22260
82 | ACCESSORY | نوارچسب نخ دار تقویت شده فیلامنت با عرض 50 میلیمتر | حلقه | 75 | 15.95 | 1196.25 | 75 | 0 | 0 | 0 | 75 | 100% | 1196.25
83 | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | کیلوگرم | 2075 | 2.65 | 5498.75 | 2075 | 0 | 0 | 0 | 2075 | 100% | 5498.75
84 | ACCESSORY | Joint Sealant Mastic JAP 81-84 | کیلوگرم | 550 | 3 | 1650 | 550 | 0 | 0 | 0 | 550 | 100% | 1650
85 | ACCESSORY | Glass Cloth Mesh | کیلوگرم | 750 | 1.3 | 975 | 750 | 0 | 0 | 0 | 750 | 100% | 975
[6 empty] | 529403.5689 | [6 empty] | 560491.9962
خلاصه محاسبات پرداخت صورت حساب: | [5 empty] | (یورو) | توضیحات:
جمع کالای دریافتی | [5 empty] | 560491.9962 | صورتحسابهای مرحله اول: MRS-JAY-098-001 الی MRS-JAY-098-009 صورتحسابهای مرحله دوم: MRS-JAY-098-010 الی MRS-JAY-098-018 صورتحسابهای مرحله سوم: MRS-JAY-098-019 الی MRS-JAY-098-025 صورتحسابهای مرحله چهارم: MRS-JAY-098-26 الی MRS-JAY-098-046 صورتحسابهای مرحله سوم به واحد مالی تحویل نشده است و محاسبات فوق با فرض عدم تسویه پارت سوم صورت گرفته است. تاریخ انعقاد قرارداد: 1401/04/22 تاریخ شروع قرارداد برابر با تاریخ ابلاغ قرارداد: 1401/04/26 تاریخ پیش پرداخت: 1401/05/09 مدت قرارداد: 60 روز تقویمی پیش از شروع قرارداد (تاخیر در پرداخت پیش پرداخت به مدت زمان تحویل اضافه می شود) سر رسید تاریخ تحویل (با توجه به توضیحات فوق): 1401/07/07 با توجه به استعلام اخذ شده از واحد برنامه ریزی، تاخیرها در ارسال اقلام با هماهنگی خریدار و تحویل طی بازه های اعلامی توسط خریدار بوده است. همچنین جمعا مبلغ 31.082/79 یورو بیشتر از سقف قرارداد کالا ارسال شده است که که مربوط به ردیف های هایلایت شده می باشد.
کسر می شود: کالای صورتحساب شده طی مراحل قبلی | [5 empty] | 463875.3507
جمع کالای دریافتی طی مراحل سوم و چهارم | [5 empty] | 96616.6455
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 8695.4981 | [10 empty] | 12942.176 | 12942.18 | 0.0039768
جمع صورتحسابهای مراحل سوم و چهارم | [5 empty] | 105312.1436
کسور:
استهلاک پیش پرداخت (باقیمانده) | [5 empty] | 19658.33
جمع کسور | [5 empty] | 19658.33
خالص قابل پرداخت (با فرض اینکه پارت سوم تسویه نشده است) | [5 empty] | 85653.8136

## Packing List Items
# | Opi No. | Date | Project Name | Packing List No. | Purchase Order | Vendor | Purchaser | Consignee | Destination | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
1 | OPI-JAY-098-001 | 2022-08-30 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-001 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 1 |  | Main Item | - | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 270 |  |  |  |  | 270 | Meter
2 | OPI-JAY-098-002 | 2022-08-30 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 2 |  | Main Item | - | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | 22 |  |  |  |  | 22 | Meter
3 | OPI-JAY-098-002 | 2022-08-30 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 2 |  | Main Item | - | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1.5 |  |  |  |  | 1.5 | Meter
4 | OPI-JAY-098-002 | 2022-08-30 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 2 |  | Main Item | - | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 3.5 |  |  |  |  | 3.5 | Meter
5 | OPI-JAY-098-002 | 2022-08-30 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 2 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 110 |  |  |  |  | 110 | Meter
6 | OPI-JAY-098-002 | 2022-08-30 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 2 |  | Main Item | - | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 132 |  |  |  |  | 132 | Meter
7 | OPI-JAY-098-002 | 2022-08-30 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 2 |  | Main Item | - | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 101 |  |  |  |  | 101 | Meter
8 | OPI-JAY-098-003 | 2022-08-30 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 3 |  | Main Item | - | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1558 |  |  |  |  | 1558 | Meter
9 | OPI-JAY-098-003 | 2022-08-30 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 3 |  | Main Item | - | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 122.5 |  |  |  |  | 122.5 | Meter
10 | OPI-JAY-098-003 | 2022-08-30 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 3 |  | Main Item | - | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 4.5 |  |  |  |  | 4.5 | Meter
11 | OPI-JAY-098-003 | 2022-08-30 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 3 |  | Main Item | - | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 37.5 |  |  |  |  | 37.5 | Meter
12 | OPI-JAY-098-003 | 2022-08-30 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 3 |  | Main Item | - | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 48.5 |  |  |  |  | 48.5 | Meter
13 | OPI-JAY-098-003 | 2022-08-30 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 3 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 84 |  |  |  |  | 84 | Meter
14 | OPI-JAY-098-005 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-004 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 4 |  | Main Item | - | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 4448.7 |  |  |  |  | 4448.7 | Sq. Meter
15 | OPI-JAY-098-005 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-004 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 4 |  | Main Item | - | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 1973.58 |  |  |  |  | 1973.58 | Sq. Meter
16 | OPI-JAY-098-004 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-005 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 5 |  | Main Item | - | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 180 |  |  |  |  | 180 | Meter |  |  | 180بسته 1متری
17 | OPI-JAY-098-006 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-006 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 6 |  | Main Item | - | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 225 |  |  |  |  | 225 | Meter
18 | OPI-JAY-098-006 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-006 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 6 |  | Main Item | - | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 36 |  |  |  |  | 36 | Meter
19 | OPI-JAY-098-007 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-007 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 7 |  | Main Item | - | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 205 |  |  |  |  | 205 | Meter
20 | OPI-JAY-098-007 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-007 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 7 |  | Main Item | - | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 204 |  |  |  |  | 204 | Meter
21 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Main Item | - | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 5869.6 |  |  |  |  | 5869.6 | Sq. Meter
22 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Main Item | - | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 2458.2 |  |  |  |  | 2458.2 | Sq. Meter
23 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Main Item | - | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 182.42 |  |  |  |  | 182.42 | Sq. Meter
24 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | تسمه استنلس استیل سایز 0/5 * 13 میلیمتر | 43500 |  |  |  |  | 43500 | Meter
25 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | تسمه استنلس استیل سایز 0/5*19 میلیمتر | 13000 |  |  |  |  | 13000 | Meter
26 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | بست استنلس استیل سایز 0/5*13 میلیمتر | 72000 |  |  |  |  | 72000 | Piece
27 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | بست استنلس استیل سایز 0/5*19میلیمتر | 3500 |  |  |  |  | 3500 | Piece
28 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 میلیمتر | 120000 |  |  |  |  | 120000 | Piece
29 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 میلیمتر | 80000 |  |  |  |  | 80000 | Piece
30 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | واشر نئو پرن | 53100 |  |  |  |  | 53100 | Piece
31 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | S کلیپس | 3200 |  |  |  |  | 3200 | Piece
32 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | سیم استنلس استیل به قطر 1 میلیمتر | 106000 |  |  |  |  | 106000 | Meter
33 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | نوار چسب نخ دار تقویت شده فیلامنت با عرض 50 میلی متر | 75 |  |  |  |  | 75 | Roll
34 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | 2075 |  |  |  |  | 2075 | Kg
35 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | Joint Sealant Mastic JAP 81-84 | 550 |  |  |  |  | 550 | Kg
36 | OPI-JAY-098-008 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | Glass Cloth Mesh | 750 |  |  |  |  | 750 | Sq. Meter
37 | OPI-JAY-098-009 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-009 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 9 |  | Main Item | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 575 |  |  |  |  | 575 | Meter
38 | OPI-JAY-098-009 | 2022-09-12 | South Adish Gas Condensate Refinery | SACR-PL-JAY-098-009 | ADSH-P-PO-GE-098 | jahanayegh | South Adish Condensate Refinery | South Adish Condensate Refinery | Adish refinery site | 9 |  | Main Item | - | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 416.5 |  |  |  |  | 416.5 | Meter

## ریز آیتم ها
# | Identity | Category | Mark No. | Description | Unit | Supply | Packing List | Receipt | PI-1 | PI-2 | PI-3 | PI-4 | Total MRS | نرخ | قراداد اولیه | 30% | نرخ تسعیر | ریال پیش پرداخت | ریال صورتحساب
1 | Bulk | - | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 277.5 | - | - |  |  |  |  | 0 | 1.077 | 298.8675 | 89.6603 | 290271 | 26025770.4278 | 0
2 | Bulk | - | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 22 | 22 | 22 |  | 22 |  |  | 22 | 1.508 | 33.176 | 9.9528 | 290271 | 2889009.2088 | 33.176
3 | Bulk | - | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1.5 | 2 | 2 |  | 1.5 |  |  | 1.5 | 2.297 | 3.4455 | 1.0336 | 290271 | 300038.6191 | 3.4455
4 | Bulk | - | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1558 | 1558 | 1558 |  | 1558 |  |  | 1558 | 1.149 | 1790.142 | 537.0426 | 290271 | 155887892.5446 | 1790.142
5 | Bulk | - | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 122.5 | 123 | 123 |  | 122.5 |  |  | 122.5 | 1.723 | 211.0675 | 63.3203 | 290271 | 18380032.2878 | 211.0675
6 | Bulk | - | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 4.5 | 5 | 5 |  | 4.5 |  |  | 4.5 | 2.44 | 10.98 | 3.294 | 290271 | 956152.674 | 10.98
7 | Bulk | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1104.5 | - | - |  |  |  |  | 0 | 1.192 | 1316.564 | 394.9692 | 290271 | 114648104.6532 | 0
8 | Bulk | - | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 323.5 | - | - |  |  |  |  | 0 | 1.795 | 580.6825 | 174.2047 | 290271 | 50566586.9873 | 0
9 | Bulk | - | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 3.5 | 4 | 4 |  | 3.5 |  |  | 3.5 | 2.656 | 9.296 | 2.7888 | 290271 | 809507.7648 | 9.296
10 | Bulk | - | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1697.5 | - | - |  |  |  |  | 0 | 1.508 | 2559.83 | 767.949 | 290271 | 222913324.179 | 0
11 | Bulk | - | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 131 | - | - |  |  |  |  | 0 | 2.104 | 275.624 | 82.6872 | 290271 | 24001696.2312 | 0
12 | Bulk | - | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1.5 | - | - |  |  |  |  | 0 | 2.943 | 4.4145 | 1.3244 | 290271 | 384420.3989 | 0
13 | Bulk | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 2009 | 110 | 110 | 110 |  |  |  | 110 | 1.579 | 3172.211 | 951.6633 | 290271 | 276240257.7543 | 173.69
14 | Bulk | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 956 | - | - |  |  |  |  | 0 | 2.44 | 2332.64 | 699.792 | 290271 | 203129323.632 | 0
15 | Bulk | - | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 37.5 | 38 | 38 | 37.5 |  |  |  | 37.5 | 3.302 | 123.825 | 37.1475 | 290271 | 10782841.9725 | 123.825
16 | Bulk | - | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1.5 | - | - |  |  |  |  | 0 | 4.235 | 6.3525 | 1.9058 | 290271 | 553183.9583 | 0
17 | Bulk | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1170.5 | 575 | 575 |  |  | 575 |  | 575 | 2.154 | 2521.257 | 756.3771 | 290271 | 219554337.1941 | 1238.55
18 | Bulk | - | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 620.5 | 621 | 621 | 204 |  | 416.5 |  | 620.5 | 3.086 | 1914.863 | 574.4589 | 290271 | 166748759.3619 | 1914.863
19 | Bulk | - | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 139 | - | - |  |  |  |  | 0 | 4.074 | 566.286 | 169.8858 | 290271 | 49312921.0518 | 0
20 | Bulk | - | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 76 | - | - |  |  |  |  | 0 | 2.496 | 189.696 | 56.9088 | 290271 | 16518974.2848 | 0
21 | Bulk | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1020 | - | - |  |  |  |  | 0 | 3.589 | 3660.78 | 1098.234 | 290271 | 318785481.414 | 0
22 | Bulk | - | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 133.5 | - | - |  |  |  |  | 0 | 4.737 | 632.3895 | 189.7168 | 290271 | 55069299.7664 | 0
23 | Bulk | - | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 68.5 | - | - |  |  |  |  | 0 | 5.956 | 407.986 | 122.3958 | 290271 | 35527951.2618 | 0
24 | Bulk | - | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 132 | 132 | 132 | 132 |  |  |  | 132 | 3.484 | 459.888 | 137.9664 | 290271 | 40047644.8944 | 459.888
25 | Bulk | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1479.5 | - | - |  |  |  |  | 0 | 4.88 | 7219.96 | 2165.988 | 290271 | 628723502.748 | 0
26 | Bulk | - | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 48.5 | 49 | 49 | 48.5 |  |  |  | 48.5 | 6.315 | 306.2775 | 91.8833 | 290271 | 26671042.8608 | 306.2775
27 | Bulk | - | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 371 | 371 | 371 | 371 |  |  |  | 371 | 7.822 | 2901.962 | 870.5886 | 290271 | 252706623.5106 | 2901.962
28 | Bulk | - | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 440 | 430 | 430 | 430 |  |  |  | 430 | 9.832 | 4326.08 | 1297.824 | 290271 | 376720670.304 | 4227.76
29 | Bulk | - | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 128 | - | - |  |  |  |  | 0 | 6.315 | 808.32 | 242.496 | 290271 | 70389556.416 | 0
|  |  | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 132 | [6 empty] | 0 | 15.892 | 2097.744 | 629.3232 | 290271 | 182674274.5872 | 0
30 | Bulk | - | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 10 | - | - |  |  |  |  | 0 | 4.339 | 43.39 | 13.017 | 290271 | 3778457.607 | 0
31 | Bulk | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 178.5 | 84 | 84 | 84 |  |  |  | 84 | 7.751 | 1383.5535 | 415.066 | 290271 | 120481637.3995 | 651.084
32 | Bulk | - | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 348 | - | - |  |  |  |  | 0 | 9.472 | 3296.256 | 988.8768 | 290271 | 287042257.6128 | 0
33 | Bulk | - | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 238 | - | - |  |  |  |  | 0 | 11.553 | 2749.614 | 824.8842 | 290271 | 239439961.6182 | 0
34 | Bulk | - | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 187 | - | - |  |  |  |  | 0 | 7.751 | 1449.437 | 434.8311 | 290271 | 126218858.2281 | 0
|  |  | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 223 | [6 empty] | 0 | 15.892 | 3543.916 | 1063.1748 | 290271 | 308608812.3708 | 0
35 | Bulk | - | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 40 | - | - |  |  |  |  | 0 | 5.134 | 205.36 | 61.608 | 290271 | 17883015.768 | 0
36 | Bulk | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 102.5 | - | - |  |  |  |  | 0 | 9.329 | 956.2225 | 286.8668 | 290271 | 83269098.3893 | 0
37 | Bulk | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 573.5 | - | - |  |  |  |  | 0 | 11.267 | 6461.6245 | 1938.4873 | 290271 | 562686661.5718 | 0
38 | Bulk | - | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 216 | 216 | 216 | 216 |  |  |  | 216 | 13.634 | 2944.944 | 883.4832 | 290271 | 256449551.9472 | 2944.944
39 | Bulk | - | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 241 | - | - |  |  |  |  | 0 | 9.329 | 2248.289 | 674.4867 | 290271 | 195783928.8957 | 0
|  |  | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 328 | [6 empty] | 0 | 15.892 | 5212.576 | 1563.7728 | 290271 | 453917894.4288 | 0
40 | Bulk | - | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 177.5 | - | - |  |  |  |  | 0 | 9.329 | 1655.8975 | 496.7692 | 290271 | 144197706.9667 | 0
|  |  |  | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 253 | [6 empty] | 0 | 16.7 | 4225.1 | 1267.53 | 290271 | 367927200.63 | 0
41 | Bulk | - | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | Meter | 1.1 | - | - |  |  |  |  | 0 | 10.888 | 11.9768 | 3.593 | 290271 | 1042955.3138 | 0
42 | Bulk | - | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 5.5 | - | - |  |  |  |  | 0 | 7.801 | 42.9055 | 12.8717 | 290271 | 3736266.7172 | 0
43 | Bulk | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 87.78 | - | - |  |  |  |  | 0 | 15.892 | 1394.9998 | 418.4999 | 290271 | 121478392.6005 | 0
44 | Bulk | - | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1007.6 | - | - |  |  |  |  | 0 | 17.508 | 17641.0608 | 5292.3182 | 290271 | 1536206507.843 | 0
45 | Bulk | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1310.1 | - | - |  |  |  |  | 0 | 18.316 | 23995.7916 | 7198.7375 | 290271 | 2089584727.0571 | 0
46 | Bulk | - | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1243 | - | - |  |  |  |  | 0 | 19.124 | 23771.132 | 7131.3396 | 290271 | 2070021077.0316 | 0
47 | Bulk | - | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 403.7 | - | - |  |  |  |  | 0 | 19.932 | 8046.5484 | 2413.9645 | 290271 | 700703895.1849 | 0
48 | Bulk | - | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 822.8 | - | - |  |  |  |  | 0 | 20.74 | 17064.872 | 5119.4616 | 290271 | 1486031238.0936 | 0
49 | Bulk | - | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 11.88 | - | - |  |  |  |  | 0 | 21.548 | 255.9902 | 76.7971 | 290271 | 22291962.8865 | 0
50 | Bulk | - | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 229.9 | - | - |  |  |  |  | 0 | 17.508 | 4025.0892 | 1207.5268 | 290271 | 350510000.152 | 0
|  |  | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 229.9 | [6 empty] | 0 | 18.316 | 4210.8484 | 1263.2545 | 290271 | 366686152.7749 | 0
51 | Bulk | - | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 5869.6 | 5870 | 5870 |  |  | 5869.6 |  | 5869.6 | 11.313 | 66402.7848 | 19920.8354 | 290271 | 5782440824.0042 | 66402.7848
52 | Bulk | - | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 6906.9 | 6907 | 6907 |  | 4448.7 | 2458.2 |  | 6906.9 | 15.084 | 104183.6796 | 31255.1039 | 290271 | 9072450258.3515 | 104183.6796
53 | Bulk | - | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 2156 | 2156 | 2156 |  | 1973.58 | 182.42 |  | 2156 | 18.855 | 40651.38 | 12195.414 | 290271 | 3539975017.194 | 40651.38
54 | Bulk | - | Insulation-Acc | Accessories for Insulation | Set | 1 | - | - |  |  |  |  | 0 |  | 0 | 0 | 290271 | 0 | 0
55 | Bulk | - | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | Meter | 1.1 | - | - |  |  |  |  | 0 | 6.341 | 6.9751 | 2.0925 | 290271 | 607400.7756 | 0
56 | Bulk | - | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | Meter | 20.9 | - | - |  |  |  |  | 0 | 6.95 | 145.255 | 43.5765 | 290271 | 12648994.2315 | 0
57 | Bulk | - | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 8.8 | - | - |  |  |  |  | 0 | 9.627 | 84.7176 | 25.4153 | 290271 | 7377318.7409 | 0
58 | Bulk | - | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 1.1 | - | - |  |  |  |  | 0 | 14.464 | 15.9104 | 4.7731 | 290271 | 1385498.3155 | 0
59 | Bulk | - | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 2.2 | - | - |  |  |  |  | 0 | 12.024 | 26.4528 | 7.9358 | 290271 | 2303544.2126 | 0
60 | Bulk | - | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 908.6 | - | - |  |  |  |  | 0 | 11.092 | 10078.1912 | 3023.4574 | 290271 | 877621991.3446 | 0
61 | Bulk | - | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 193.6 | - | - |  |  |  |  | 0 | 14.626 | 2831.5936 | 849.4781 | 290271 | 246578851.7597 | 0
62 | Bulk | - | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 85.8 | - | - |  |  |  |  | 0 | 21.123 | 1812.3534 | 543.706 | 290271 | 157822090.1314 | 0
63 | Bulk | - | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 34.1 | - | - |  |  |  |  | 0 | 25.184 | 858.7744 | 257.6323 | 290271 | 74783191.1587 | 0
64 | Bulk | - | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 38.5 | - | - |  |  |  |  | 0 | 33.513 | 1290.2505 | 387.0751 | 290271 | 112356690.8656 | 0
65 | Bulk | - | 4YYYYYE06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | Meter | 125.4 | - | - |  |  |  |  | 0 | 56.052 | 7028.9208 | 2108.6762 | 290271 | 612087560.861 | 0
66 | Bulk | - | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | Meter | 39.6 | - | - |  |  |  |  | 0 | 44.68 | 1769.328 | 530.7984 | 290271 | 154075382.3664 | 0
|  |  | ACCESSORY | تسمه استنلس استیل سایز 13mm*0/5mm | Meter | 43500 | [5 empty] | 43500 | 43500 | 0.61 | 26535 | 7960.5 | 294059 | 2340856669.5 | 26535
|  |  | ACCESSORY | تسمه استنلس استیل سایز 19mm*0/5mm | Meter | 13000 | [5 empty] | 13000 | 13000 | 1 | 13000 | 3900 | 294059 | 1146830100 | 13000
|  |  | ACCESSORY | بست استنلس استیل سایز 13mm*0/5mm | pcs | 72000 | [5 empty] | 72000 | 72000 | 0.08 | 5760 | 1728 | 294059 | 508133952 | 5760
|  |  | ACCESSORY | بست استنلس استیل سایز 19mm*0/5mm | pcs | 3500 | [5 empty] | 3500 | 3500 | 0.08 | 280 | 84 | 294059 | 24700956 | 280
|  |  | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 | pcs | 120000 | [5 empty] | 120000 | 120000 | 0.066 | 7920 | 2376 | 294059 | 698684184 | 7920
|  |  | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 | pcs | 80000 | [5 empty] | 80000 | 80000 | 0.057 | 4560 | 1368 | 294059 | 402272712 | 4560
|  |  | ACCESSORY | واشر لئوپرن | pcs | 120000 | [5 empty] | 53100 | 53100 | 0.036 | 4320 | 1296 | 294059 | 381100464 | 1911.6
|  |  | ACCESSORY | ماستیک METAL SEALANT | pcs | 3090 | [6 empty] | 0 | 6.6 | 20394 | 6118.2 | 294059 | 1799111773.8 | 0
|  |  | ACCESSORY | کلیپس S | pcs | 3200 | [5 empty] | 3200 | 3200 | 0.09 | 288 | 86.4 | 294059 | 25406697.6 | 288
|  |  | ACCESSORY | سیم استنلس استیل به قطر 1mm | Meter | 106000 | [5 empty] | 106000 | 106000 | 0.21 | 22260 | 6678 | 294059 | 1963726002 | 22260
|  |  | ACCESSORY | نوارچسب نخ دار تقویت شده فیلامنت با عرض 50 میلیمتر | Roll | 75 | [5 empty] | 75 | 75 | 15.95 | 1196.25 | 358.875 | 294059 | 105530423.625 | 1196.25
|  |  | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | Kg | 2075 | [5 empty] | 2075 | 2075 | 2.65 | 5498.75 | 1649.625 | 294059 | 485087077.875 | 5498.75
|  |  | ACCESSORY | Joint Sealant Mastic JAP 81-84 | Kg | 550 | [5 empty] | 550 | 550 | 3 | 1650 | 495 | 294059 | 145559205 | 1650
|  |  | ACCESSORY | Glass Cloth Mesh | Kg | 750 | [5 empty] | 750 | 750 | 1.3 | 975 | 292.5 | 294059 | 86012257.5 | 975