## VDLS
Item No. | Purchase Order | Vendor | Discipline | Type | Class | Document Number | Vendor Number | Purchaser Number | Document Title | Weight Factor | First Issue (Baseline) | First Issue Delay | Last Issue | [12 empty] | Weight Factor | Progress | 1st Issue | [13 empty] | 2nd Issue | [13 empty] | 3rd Issue | [13 empty] | 4th Issue | [13 empty] | 5th Issue | [13 empty] | 6th Issue | [13 empty] | 7th Issue | [13 empty] | 8th Issue | [13 empty] | 9th Issue | [13 empty] | 10th Issue | [13 empty] | 11th Issue | [13 empty] | 12th Issue | [13 empty] | 13th Issue | [13 empty] | 14th Issue | [13 empty] | 15th Issue | [13 empty] | 16th Issue | [13 empty] | 17th Issue | [13 empty] | 18th Issue | [13 empty] | 19th Issue | [13 empty] | 20th Issue
[13 empty] | Vendor |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion |  |  | Vendor |  |  |  |  | Purchaser/Client |  |  | Vendor |  |  | End Conclusion
[13 empty] | Rev. | POI | Transmittal No | Transmittal Date. | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status |  |  | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status | Revision | POI | Transmittal No | Transmittal Date | Transmittal Date Farsi | Comment No. | Comment Date | Comment Status | Reply No. | Reply Date | Reply Status | No. | Date | Status
1 | ADSH-P-PO-GE-020 | SPH | EL | DSH | 1 | SACR-306-CWS-EL-DSH-0033 |  |  | MOTOR DATA SHEET FOR COOLING TOWER | 0 | - |  | 04 | FIN | SACR-020-SPH-AH-T-0043 | 2022-01-11 | SACR-306-CWS-EL-DSH-0033-04-05 | 2022-02-07 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0016 | 2020-02-11 | 1398/11/22 | SACR-306-CWS-EL-DSH-0033-00-07 | 2020-02-24 | RJ | SACR-306-CWS-EL-DSH-0033-00-08 | 2020-03-02 | Noted |  |  |  | 00 | IFA | SACR-020-1491-AH-T-0029 | 2020-03-02 | 1398/12/12 | SACR-306-CWS-EL-DSH-0033-00-15 | 2020-03-11 | RJ | SACR-306-CWS-EL-DSH-0033-00-16 | 2020-03-20 | Noted |  |  |  | 00 | IFA | SACR-020-1491-AH-T-0043 | 2020-03-20 | 1399/01/01 | SACR-306-CWS-EL-DSH-0033-00-23 | 2020-04-04 | CO | SACR-306-CWS-EL-DSH-0033-00-24 | 2020-04-08 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0056 | 2020-04-08 | 1399/01/20 | SACR-306-CWS-EL-DSH-0033-01-06 | 2020-04-18 | CO | SACR-306-CWS-EL-DSH-0033-01-07 | 2020-04-20 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0063 | 2020-04-20 | 1399/02/01 | SACR-306-CWS-EL-DSH-0033-02-03 | 2020-04-29 | APN | SACR-306-CWS-EL-DSH-0033-02-06 | 2021-11-03 | Noted |  |  |  | 03 | FIN | SACR-020-SPH-AH-T-0041 | 2021-11-09 | 1400/08/18 | SACR-306-CWS-EL-DSH-0033-03-08 | 2022-01-09 | AP | [6 empty] | 04 | FIN | SACR-020-SPH-AH-T-0043 | 2022-01-11 | 1400/10/21 | SACR-306-CWS-EL-DSH-0033-04-05 | 2022-02-07 | AP
2 | ADSH-P-PO-GE-020 | SPH | EL | DWG | 1 | SACR-306-CWS-EL-DWG-0034 |  |  | Motor dimensional outline drawing and Name plate drawing | 0 | - |  | 00 | IFA | SACR-020-1491-AH-T-0017 | 2020-02-11 | SACR-306-CWS-EL-DWG-0034-00-07 | 2020-02-23 | CO | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0017 | 2020-02-11 | 1398/11/22 | SACR-306-CWS-EL-DWG-0034-00-07 | 2020-02-23 | CO
3 | ADSH-P-PO-GE-020 | SPH | EL | DWG | 1 | SACR-306-CWS-EL-DWG-0036 |  |  | Starting time current curve (100% Voltage) | 0 | - |  | 00 | IFA | SACR-020-1491-AH-T-0030 | 2020-03-04 | SACR-306-CWS-EL-DWG-0036-00-15 | 2020-03-14 | APN | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0019 | 2020-02-12 | 1398/11/23 | SACR-306-CWS-EL-DWG-0036-00-06 | 2020-02-23 | RJ | SACR-306-CWS-EL-DWG-0036-00-07 | 2020-03-04 | Noted |  |  |  | 00 | IFA | SACR-020-1491-AH-T-0030 | 2020-03-04 | 1398/12/14 | SACR-306-CWS-EL-DWG-0036-00-15 | 2020-03-14 | APN
4 | ADSH-P-PO-GE-020 | SPH | EL | DWG | 1 | SACR-306-CWS-EL-DWG-0117 |  |  | Detail drawing Of Motor cover, Coupling cover and Shaft Guard | 0 | - | 738780
5 | ADSH-P-PO-GE-020 | SPH | EL | DWG | 1 | SACR-306-CWS-EL-DWG-0118 |  |  | Detail drawing for Motor & Gearbox Support For Cooling Tower | 0 | - | 738780
6 | ADSH-P-PO-GE-020 | SPH | EL | DWG | 1 | SACR-306-CWS-EL-DWG-0136 |  |  | Motor drawing details | 0 | - |  | 00 | IFA | SACR-020-SPH-AH-T-0046 | 2022-03-16 | SACR-306-CWS-EL-DWG-0136-00-04 | 2022-03-27 | APN | [8 empty] | 00 | IFA | SACR-020-SPH-AH-T-0046 | 2022-03-16 | 1400/12/25 | SACR-306-CWS-EL-DWG-0136-00-04 | 2022-03-27 | APN
7 | ADSH-P-PO-GE-020 | SPH | EL | LAY | 1 | SACR-306-CWS-EL-LAY-0038 |  |  | Cable routing layout (inside the tower) | 0 | - |  | 03 | IFA | SACR-020-1491-AH-T-0210 | 2020-11-11 | SACR-306-CWS-EL-LAY-0038-03-06 | 2020-11-18 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0129 | 2020-07-22 | 1399/05/01 | SACR-306-CWS-EL-LAY-0038-00-08 | 2020-08-05 | CO | SACR-306-CWS-EL-LAY-0038-00-09 | 2020-08-16 | Noted |  |  |  | 01 | FIN | SACR-020-1491-AH-T-0152 | 2020-08-16 | 1399/05/26 | SACR-306-CWS-EL-LAY-0038-01-04 | 2020-08-24 | APN | SACR-306-CWS-EL-LAY-0038-01-05 | 2020-10-27 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0202 | 2020-10-27 | 1399/08/06 | SACR-306-CWS-EL-LAY-0038-02-04 | 2020-11-08 | APN | SACR-306-CWS-EL-LAY-0038-02-05 | 2020-11-11 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0210 | 2020-11-11 | 1399/08/21 | SACR-306-CWS-EL-LAY-0038-03-06 | 2020-11-18 | AP
8 | ADSH-P-PO-GE-020 | SPH | EL | LAY | 1 | SACR-306-CWS-EL-LAY-0049 |  |  | Earthing layout (inside the tower) | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0189 | 2020-10-05 | SACR-306-CWS-EL-LAY-0049-02-03 | 2020-10-05 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0128 | 2020-07-22 | 1399/05/01 | SACR-306-CWS-EL-LAY-0049-00-04 | 2020-08-05 | CO | SACR-306-CWS-EL-LAY-0049-00-05 | 2020-08-16 | Noted |  |  |  | 01 | FIN | SACR-020-1491-AH-T-0153 | 2020-08-16 | 1399/05/26 | SACR-306-CWS-EL-LAY-0049-01-04 | 2020-08-24 | APN | SACR-306-CWS-EL-LAY-0049-01-05 | 2020-10-05 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0189 | 2020-10-05 | 1399/07/14 | SACR-306-CWS-EL-LAY-0049-02-03 | 2020-10-05 | AP
9 | ADSH-P-PO-GE-020 | SPH | EL | LST | 1 | SACR-306-CWS-EL-LST-0031 |  |  | Electrical Load List | 0 | - |  | 01 | FIN | SACR-020-1491-AH-T-0133 | 2020-07-29 | SACR-306-CWS-EL-LST-0031-01-04 | 2020-08-09 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0130 | 2020-07-22 | 1399/05/01 | SACR-306-CWS-EL-LST-0031-00-04 | 2020-07-28 | CO | SACR-306-CWS-EL-LST-0031-00-05 | 2020-07-29 | Noted |  |  |  | 01 | FIN | SACR-020-1491-AH-T-0133 | 2020-07-29 | 1399/05/08 | SACR-306-CWS-EL-LST-0031-01-04 | 2020-08-09 | AP
10 | ADSH-P-PO-GE-020 | SPH | EL | LST | 1 | SACR-306-CWS-EL-LST-0042 |  |  | Cable list for cooling tower | 0 | - |  | 00 | IFA | SACR-020-1491-AH-T-0251 | 2020-12-28 | SACR-306-CWS-EL-LST-0042-00-05 | 2021-01-05 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0251 | 2020-12-28 | 1399/10/08 | SACR-306-CWS-EL-LST-0042-00-05 | 2021-01-05 | AP
11 | ADSH-P-PO-GE-020 | SPH | IN | DIA | 1 | SACR-306-CWS-IN-DIA-0059 |  |  | Logic Diagram and Control Philosophy and Narrative | 0 | - |  | 03 | IFA | SACR-020-1491-AH-T-0201 | 2020-10-27 | SACR-306-CWS-IN-DIA-0059-03-03 | 2020-10-28 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0121 | 2020-07-18 | 1399/04/28 | SACR-306-CWS-IN-DIA-0059-00-09 | 2020-07-28 | CO | SACR-306-CWS-IN-DIA-0059-00-11 | 2020-08-16 | Noted |  |  |  | 01 | FIN | SACR-020-1491-AH-T-0154 | 2020-08-16 | 1399/05/26 | SACR-306-CWS-IN-DIA-0059-01-05 | 2020-08-22 | CO | SACR-306-CWS-IN-DIA-0059-01-06 | 2020-08-22 | Noted |  |  |  | 02 | FIN | SACR-020-1491-AH-T-0157 | 2020-08-22 | 1399/06/01 | SACR-306-CWS-IN-DIA-0059-02-04 | 2020-08-31 | CO | SACR-306-CWS-IN-DIA-0059-02-05 | 2020-10-27 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0201 | 2020-10-27 | 1399/08/06 | SACR-306-CWS-IN-DIA-0059-03-03 | 2020-10-28 | AP
12 | ADSH-P-PO-GE-020 | SPH | IN | DSH | 1 | SACR-306-CWS-IN-DSH-0052 |  |  | Instrument data sheet | 0 | - |  | 03 | IFA | SACR-020-1491-AH-T-0197 | 2020-10-20 | SACR-306-CWS-IN-DSH-0052-03-03 | 2020-10-21 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0119 | 2020-07-18 | 1399/04/28 | SACR-306-CWS-IN-DSH-0052-00-06 | 2020-07-28 | CO | SACR-306-CWS-IN-DSH-0052-00-07 | 2020-08-09 | Noted |  |  |  | 01 | FIN | SACR-020-1491-AH-T-0137 | 2020-08-09 | 1399/05/19 | SACR-306-CWS-IN-DSH-0052-01-04 | 2020-08-17 | CO | SACR-306-CWS-IN-DSH-0052-01-05 | 2020-10-06 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0192 | 2020-10-06 | 1399/07/15 | SACR-306-CWS-IN-DSH-0052-02-04 | 2020-10-12 | CO | SACR-306-CWS-IN-DSH-0052-02-05 | 2020-10-20 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0197 | 2020-10-20 | 1399/07/29 | SACR-306-CWS-IN-DSH-0052-03-03 | 2020-10-21 | AP
13 | ADSH-P-PO-GE-020 | SPH | IN | DWG | 1 | SACR-306-CWS-IN-DWG-0079 |  |  | Instrument hook up drawing for cooling tower | 0 | - |  | 02 | FIN | SACR-020-1491-AH-T-0284 | 2021-02-01 | SACR-306-CWS-IN-DWG-0079-02-04 | 2021-02-09 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0123 | 2020-07-18 | 1399/04/28 | SACR-306-CWS-IN-DWG-0079-00-06 | 2020-07-28 | CO | SACR-306-CWS-IN-DWG-0079-00-07 | 2020-08-12 | Noted |  |  |  | 01 | FIN | SACR-020-1491-AH-T-0150 | 2020-08-12 | 1399/05/22 | SACR-306-CWS-IN-DWG-0079-01-04 | 2020-08-23 | APN | SACR-306-CWS-IN-DWG-0079-01-05 | 2021-02-01 | Noted |  |  |  | 02 | FIN | SACR-020-1491-AH-T-0284 | 2021-02-01 | 1399/11/13 | SACR-306-CWS-IN-DWG-0079-02-04 | 2021-02-09 | AP
14 | ADSH-P-PO-GE-020 | SPH | IN | LAY | 1 | SACR-306-CWS-IN-LAY-0078 |  |  | Instrument location layout for cooling tower | 0 | - |  | 01 | IFA | SACR-020-1491-AH-T-0295 | 2021-02-14 | SACR-306-CWS-IN-LAY-0078-01-08 | 2021-02-20 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0122 | 2020-07-18 | 1399/04/28 | SACR-306-CWS-IN-LAY-0078-00-06 | 2020-07-28 | CO | SACR-306-CWS-IN-LAY-0078-00-07 | 2021-02-14 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0295 | 2021-02-14 | 1399/11/26 | SACR-306-CWS-IN-LAY-0078-01-08 | 2021-02-20 | AP
15 | ADSH-P-PO-GE-020 | SPH | IN | LST | 1 | SACR-306-CWS-IN-LST-0051 |  |  | Instrument list & index | 0 | - |  | 04 | IFA | SACR-020-1491-AH-T-0198 | 2020-10-20 | SACR-306-CWS-IN-LST-0051-04-03 | 2020-10-21 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0120 | 2020-07-18 | 1399/04/28 | SACR-306-CWS-IN-LST-0051-00-07 | 2020-07-29 | CO | SACR-306-CWS-IN-LST-0051-00-08 | 2020-08-10 | Noted |  |  |  | 01 | FIN | SACR-020-1491-AH-T-0141 | 2020-08-10 | 1399/05/20 | SACR-306-CWS-IN-LST-0051-01-04 | 2020-08-17 | CO | SACR-306-CWS-IN-LST-0051-01-05 | 2020-08-26 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0161 | 2020-08-26 | 1399/06/05 | SACR-306-CWS-IN-LST-0051-02-06 | 2020-09-06 | APN | SACR-306-CWS-IN-LST-0051-02-07 | 2020-10-05 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0190 | 2020-10-05 | 1399/07/14 | SACR-306-CWS-IN-LST-0051-03-04 | 2020-10-12 | CO | SACR-306-CWS-IN-LST-0051-03-05 | 2020-10-20 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0198 | 2020-10-20 | 1399/07/29 | SACR-306-CWS-IN-LST-0051-04-03 | 2020-10-21 | AP
16 | ADSH-P-PO-GE-020 | SPH | IN | LST | 1 | SACR-306-CWS-IN-LST-0053 |  |  | I/O List for Cooling Tower | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0172 | 2020-09-12 | SACR-306-CWS-IN-LST-0053-02-04 | 2020-09-21 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0127 | 2020-07-19 | 1399/04/29 | SACR-306-CWS-IN-LST-0053-00-06 | 2020-07-28 | CO | SACR-306-CWS-IN-LST-0053-00-07 | 2020-08-10 | Noted |  |  |  | 01 | FIN | SACR-020-1491-AH-T-0142 | 2020-08-10 | 1399/05/20 | SACR-306-CWS-IN-LST-0053-01-04 | 2020-08-22 | APN | SACR-306-CWS-IN-LST-0053-01-05 | 2020-09-12 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0172 | 2020-09-12 | 1399/06/22 | SACR-306-CWS-IN-LST-0053-02-04 | 2020-09-21 | AP
17 | ADSH-P-PO-GE-020 | SPH | IN | LST | 1 | SACR-306-CWS-IN-LST-0060 |  |  | Alarm and Set Point List | 0 | - |  | 02 | FIN | SACR-020-1491-AH-T-0300 | 2021-02-15 | SACR-306-CWS-IN-LST-0060-02-07 | 2021-02-27 | AP | [8 empty] | 00 | FIN | SACR-020-1491-AH-T-0136 | 2020-08-09 | 1399/05/19 | SACR-306-CWS-IN-LST-0060-00-11 | 2020-08-22 | APN | SACR-306-CWS-IN-LST-0060-00-12 | 2021-01-04 | Replied | SACR-306-CWS-IN-LST-0060-00-15 | 2021-01-13 | RJ | 00 | FIN | SACR-020-1491-AH-T-0264 | 2021-01-16 | 1399/10/27 | SACR-306-CWS-IN-LST-0060-00-23 | 2021-01-30 | APN | SACR-306-CWS-IN-LST-0060-00-24 | 2021-02-01 | Noted |  |  |  | 01 | FIN | SACR-020-1491-AH-T-0283 | 2021-02-01 | 1399/11/13 | SACR-306-CWS-IN-LST-0060-01-08 | 2021-02-09 | APN | SACR-306-CWS-IN-LST-0060-01-09 | 2021-02-15 | Noted |  |  |  | 02 | FIN | SACR-020-1491-AH-T-0300 | 2021-02-15 | 1399/11/27 | SACR-306-CWS-IN-LST-0060-02-07 | 2021-02-27 | AP
18 | ADSH-P-PO-GE-020 | SPH | MA | CER | 1 | SACR-306-CWS-MA-CER-0068 |  |  | Certificates of guarantee and compliance | 0 | - | 738780
19 | ADSH-P-PO-GE-020 | SPH | MA | CSH | 1 | SACR-306-CWS-MA-CSH-0045 |  |  | Strength Calculation Sheet For Drive Shaft Equipment For Cooling Tower | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0196 | 2020-10-11 | SACR-306-CWS-MA-CSH-0045-02-04 | 2020-10-15 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0089 | 2020-05-18 | 1399/02/29 | SACR-306-CWS-MA-CSH-0045-00-04 | 2020-05-30 | CO | SACR-306-CWS-MA-CSH-0045-00-05 | 2020-07-19 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0126 | 2020-07-19 | 1399/04/29 | SACR-306-CWS-MA-CSH-0045-01-04 | 2020-07-25 | RJ | SACR-306-CWS-MA-CSH-0045-01-05 | 2020-08-11 | Noted |  |  |  | 01 | FIN | SACR-020-1491-AH-T-0147 | 2020-08-11 | 1399/05/21 | SACR-306-CWS-MA-CSH-0045-01-08 | 2020-08-11 | RJ | SACR-306-CWS-MA-CSH-0045-01-09 | 2020-08-11 | Noted |  |  |  | 01 | FIN | SACR-020-1491-AH-T-0148 | 2020-08-11 | 1399/05/21 | SACR-306-CWS-MA-CSH-0045-01-14 | 2020-08-15 | CO | SACR-306-CWS-MA-CSH-0045-01-15 | 2020-10-11 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0196 | 2020-10-11 | 1399/07/20 | SACR-306-CWS-MA-CSH-0045-02-04 | 2020-10-15 | AP
20 | ADSH-P-PO-GE-020 | SPH | MA | CSH | 1 | SACR-306-CWS-MA-CSH-0087 |  |  | Thermal Calculations of Evaporative Counter Flow Cooling Tower & Associated Mechanical Components | 0 | - |  | 04 | IFA | SACR-020-1491-AH-T-0054 | 2020-04-06 | SACR-306-CWS-MA-CSH-0087-04-03 | 2020-04-06 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0018 | 2020-02-12 | 1398/11/23 | SACR-306-CWS-MA-CSH-0087-00-07 | 2020-02-24 | CO | SACR-306-CWS-MA-CSH-0087-00-08 | 2020-03-02 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0027 | 2020-03-02 | 1398/12/12 | SACR-306-CWS-MA-CSH-0087-01-07 | 2020-03-15 | CO | SACR-306-CWS-MA-CSH-0087-01-08 | 2020-03-25 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0046 | 2020-03-25 | 1399/01/06 | SACR-306-CWS-MA-CSH-0087-02-04 | 2020-03-29 | CO | SACR-306-CWS-MA-CSH-0087-02-05 | 2020-04-02 | Replied | SACR-306-CWS-MA-CSH-0087-02-07 | 2020-04-03 | CO | 03 | IFA | SACR-020-1491-AH-T-0053 | 2020-04-05 | 1399/01/17 | SACR-306-CWS-MA-CSH-0087-03-03 | 2020-04-06 | APN | SACR-306-CWS-MA-CSH-0087-03-04 | 2020-04-06 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0054 | 2020-04-06 | 1399/01/18 | SACR-306-CWS-MA-CSH-0087-04-03 | 2020-04-06 | AP
21 | ADSH-P-PO-GE-020 | SPH | MA | DSH | 1 | SACR-306-CWS-MA-DSH-0019 |  |  | Data sheet for Gearbox for cooling tower | 0 | - |  | 04 | IFA | SACR-020-1491-AH-T-0124 | 2020-07-19 | SACR-306-CWS-MA-DSH-0019-04-10 | 2020-08-09 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0025 | 2020-02-29 | 1398/12/10 | SACR-306-CWS-MA-DSH-0019-00-06 | 2020-03-11 | CO | SACR-306-CWS-MA-DSH-0019-00-07 | 2020-03-18 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0042 | 2020-03-18 | 1398/12/28 | SACR-306-CWS-MA-DSH-0019-01-05 | 2020-03-27 | CO | SACR-306-CWS-MA-DSH-0019-01-06 | 2020-05-08 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0087 | 2020-05-16 | 1399/02/27 | SACR-306-CWS-MA-DSH-0019-02-07 | 2020-05-26 | CO | SACR-306-CWS-MA-DSH-0019-02-08 | 2020-06-13 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0105 | 2020-06-13 | 1399/03/24 | SACR-306-CWS-MA-DSH-0019-03-07 | 2020-06-21 | RJ | SACR-306-CWS-MA-DSH-0019-03-08 | 2020-07-12 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0115 | 2020-07-12 | 1399/04/22 | SACR-306-CWS-MA-DSH-0019-03-13 | 2020-07-18 | CO | SACR-306-CWS-MA-DSH-0019-03-14 | 2020-07-19 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0124 | 2020-07-19 | 1399/04/29 | SACR-306-CWS-MA-DSH-0019-04-10 | 2020-08-09 | AP
22 | ADSH-P-PO-GE-020 | SPH | MA | DSH | 1 | SACR-306-CWS-MA-DSH-0020 |  |  | Data sheet for Fan for cooling tower | 0 | - |  | 07 | FIN | SACR-020-1491-AH-T-0302 | 2021-02-20 | SACR-306-CWS-MA-DSH-0020-07-07 | 2021-02-27 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0015 | 2020-02-11 | 1398/11/22 | SACR-306-CWS-MA-DSH-0020-00-08 | 2020-02-24 | RJ | SACR-306-CWS-MA-DSH-0020-00-09 | 2020-02-29 | Noted |  |  |  | 00 | IFA | SACR-020-1491-AH-T-0024 | 2020-02-29 | 1398/12/10 | SACR-306-CWS-MA-DSH-0020-00-17 | 2020-03-15 | CO | SACR-306-CWS-MA-DSH-0020-00-18 | 2020-03-22 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0044 | 2020-03-22 | 1399/01/03 | SACR-306-CWS-MA-DSH-0020-01-03 | 2020-03-25 | CO | SACR-306-CWS-MA-DSH-0020-01-04 | 2020-04-10 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0057 | 2020-04-10 | 1399/01/22 | SACR-306-CWS-MA-DSH-0020-02-04 | 2020-04-18 | CO | SACR-306-CWS-MA-DSH-0020-02-05 | 2020-04-19 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0062 | 2020-04-19 | 1399/01/31 | SACR-306-CWS-MA-DSH-0020-03-05 | 2020-04-25 | APN | SACR-306-CWS-MA-DSH-0020-03-06 | 2020-05-18 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0090 | 2020-05-19 | 1399/02/30 | SACR-306-CWS-MA-DSH-0020-04-12 | 2020-05-30 | APN | SACR-306-CWS-MA-DSH-0020-04-13 | 2020-07-08 | Noted |  |  |  | 05 | IFA | SACR-020-1491-AH-T-0113 | 2020-07-08 | 1399/04/18 | SACR-306-CWS-MA-DSH-0020-05-05 | 2020-07-18 | APN | SACR-306-CWS-MA-DSH-0020-05-06 | 2020-07-19 | Noted |  |  |  | 06 | IFA | SACR-020-1491-AH-T-0125 | 2020-07-19 | 1399/04/29 | SACR-306-CWS-MA-DSH-0020-06-06 | 2020-08-09 | APN | SACR-306-CWS-MA-DSH-0020-06-07 | 2021-02-20 | Noted |  |  |  | 07 | FIN | SACR-020-1491-AH-T-0302 | 2021-02-20 | 1399/12/02 | SACR-306-CWS-MA-DSH-0020-07-07 | 2021-02-27 | AP
23 | ADSH-P-PO-GE-020 | SPH | MA | DSH | 1 | SACR-306-CWS-MA-DSH-0127 |  |  | Data Sheets & Technical Specification Of Drive Shaft For Cooling Tower | 0 | - |  | 02 | FIN | SACR-020-1491-AH-T-0138 | 2020-08-09 | SACR-306-CWS-MA-DSH-0127-02-06 | 2020-08-16 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0084 | 2020-05-16 | 1399/02/27 | SACR-306-CWS-MA-DSH-0127-00-04 | 2020-05-26 | APN | SACR-306-CWS-MA-DSH-0127-00-05 | 2020-07-11 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0114 | 2020-07-11 | 1399/04/21 | SACR-306-CWS-MA-DSH-0127-01-04 | 2020-07-27 | APN | SACR-306-CWS-MA-DSH-0127-01-05 | 2020-07-28 | Noted |  |  |  | 02 | FIN | SACR-020-1491-AH-T-0138 | 2020-08-09 | 1399/05/19 | SACR-306-CWS-MA-DSH-0127-02-06 | 2020-08-16 | AP
24 | ADSH-P-PO-GE-020 | SPH | MA | DSH | 1 | SACR-306-CWS-MA-DSH-0132 |  |  | The cooling tower datasheet | 0 | - |  | 05 | FIN | SACR-020-1491-AH-T-0303 | 2021-02-21 | SACR-306-CWS-MA-DSH-0132-05-05 | 2021-03-09 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0047 | 2020-03-27 | 1399/01/08 | SACR-306-CWS-MA-DSH-0132-00-04 | 2020-04-04 | CO | SACR-306-CWS-MA-DSH-0132-00-05 | 2020-04-07 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0055 | 2020-04-08 | 1399/01/20 | SACR-306-CWS-MA-DSH-0132-01-09 | 2020-04-25 | CO | SACR-306-CWS-MA-DSH-0132-01-10 | 2020-05-01 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0073 | 2020-05-01 | 1399/02/12 | SACR-306-CWS-MA-DSH-0132-02-08 | 2020-05-14 | APN | SACR-306-CWS-MA-DSH-0132-02-09 | 2020-05-16 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0088 | 2020-05-17 | 1399/02/28 | SACR-306-CWS-MA-DSH-0132-03-09 | 2020-06-01 | AP | [6 empty] | 04 | FIN | SACR-020-1491-AH-T-0294 | 2021-02-09 | 1399/11/21 | SACR-306-CWS-MA-DSH-0132-04-10 | 2021-02-21 | CO | SACR-306-CWS-MA-DSH-0132-04-11 | 2021-02-21 | Noted |  |  |  | 05 | FIN | SACR-020-1491-AH-T-0303 | 2021-02-21 | 1399/12/03 | SACR-306-CWS-MA-DSH-0132-05-05 | 2021-03-09 | AP
25 | ADSH-P-PO-GE-020 | SPH | MA | DWG | 1 | SACR-306-CWS-MA-DWG-0003 |  |  | Penstock detail drawing for cooling tower | 0 | - |  | 08 | FIN | SACR-020-SPH-AH-T-0016 | 2021-04-19 | SACR-306-CWS-MA-DWG-0003-08-09 | 2021-04-20 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0094 | 2020-05-23 | 1399/03/03 | SACR-306-CWS-MA-DWG-0003-00-04 | 2020-05-31 | RJ | SACR-306-CWS-MA-DWG-0003-00-05 | 2020-08-18 | Noted |  |  |  | 00 | IFA | SACR-020-1491-AH-T-0155 | 2020-08-18 | 1399/05/28 | SACR-306-CWS-MA-DWG-0003-00-14 | 2020-09-06 | CO | SACR-306-CWS-MA-DWG-0003-00-15 | 2020-11-07 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0208 | 2020-11-07 | 1399/08/17 | SACR-306-CWS-MA-DWG-0003-01-05 | 2020-11-14 | APN | SACR-306-CWS-MA-DWG-0003-01-06 | 2020-11-18 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0212 | 2020-11-18 | 1399/08/28 | SACR-306-CWS-MA-DWG-0003-02-06 | 2020-12-05 | AP | [6 empty] | 03 | IFA | SACR-020-1491-AH-T-0245 | 2020-12-23 | 1399/10/03 | SACR-306-CWS-MA-DWG-0003-03-06 | 2021-01-02 | CO | SACR-306-CWS-MA-DWG-0003-03-07 | 2021-01-06 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0257 | 2021-01-06 | 1399/10/17 | SACR-306-CWS-MA-DWG-0003-04-05 | 2021-01-13 | CO | SACR-306-CWS-MA-DWG-0003-04-06 | 2021-02-14 | Noted |  |  |  | 05 | IFA | SACR-020-1491-AH-T-0296 | 2021-02-14 | 1399/11/26 | SACR-306-CWS-MA-DWG-0003-05-05 | 2021-02-24 | AP | [6 empty] | 06 | IFA | SACR-020-SPH-AH-T-0012 | 2021-04-06 | 1400/01/17 | SACR-306-CWS-MA-DWG-0003-06-08 | 2021-04-17 | APN | SACR-306-CWS-MA-DWG-0003-06-09 | 2021-04-18 | Noted |  |  |  | 07 | FIN | SACR-020-SPH-AH-T-0015 | 2021-04-18 | 1400/01/29 | SACR-306-CWS-MA-DWG-0003-07-05 | 2021-04-19 | APN | SACR-306-CWS-MA-DWG-0003-07-06 | 2021-04-19 | Noted |  |  |  | 08 | FIN | SACR-020-SPH-AH-T-0016 | 2021-04-19 | 1400/01/30 | SACR-306-CWS-MA-DWG-0003-08-09 | 2021-04-20 | AP
26 | ADSH-P-PO-GE-020 | SPH | MA | DWG | 1 | SACR-306-CWS-MA-DWG-0021 |  |  | Performance curves FOR COOLING WATER SYSTEM | 0 | - |  | 01 | IFA | SACR-020-1491-AH-T-0282 | 2021-02-01 | SACR-306-CWS-MA-DWG-0021-01-08 | 2021-02-13 | CO | [8 empty] | 00 | IFI | SACR-020-1491-AH-T-0267 | 2021-01-20 | 1399/11/01 | SACR-306-CWS-MA-DWG-0021-00-07 | 2021-01-30 | CO | SACR-306-CWS-MA-DWG-0021-00-08 | 2021-02-01 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0282 | 2021-02-01 | 1399/11/13 | SACR-306-CWS-MA-DWG-0021-01-08 | 2021-02-13 | CO
27 | ADSH-P-PO-GE-020 | SPH | MA | DWG | 1 | SACR-306-CWS-MA-DWG-0115 |  |  | Detail drawing Of Lubricant Assembly | 0 | - | 738780
28 | ADSH-P-PO-GE-020 | SPH | MA | DWG | 1 | SACR-306-CWS-MA-DWG-0116 |  |  | Detail drawing Of Fan Stack | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0271 | 2021-01-23 | SACR-306-CWS-MA-DWG-0116-02-08 | 2021-02-03 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0216 | 2020-11-26 | 1399/09/06 | SACR-306-CWS-MA-DWG-0116-00-05 | 2020-12-05 | CO | SACR-306-CWS-MA-DWG-0116-00-06 | 2020-12-14 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0237 | 2020-12-14 | 1399/09/24 | SACR-306-CWS-MA-DWG-0116-01-05 | 2020-12-26 | CO | SACR-306-CWS-MA-DWG-0116-01-06 | 2021-01-02 | Replied | SACR-306-CWS-MA-DWG-0116-01-09 | 2021-01-02 | CO | 02 | IFA | SACR-020-1491-AH-T-0271 | 2021-01-23 | 1399/11/04 | SACR-306-CWS-MA-DWG-0116-02-08 | 2021-02-03 | AP
29 | ADSH-P-PO-GE-020 | SPH | MA | DWG | 1 | SACR-306-CWS-MA-DWG-0117 |  |  | Detail drawing Of Drift Eliminator | 0 | - |  | 04 | IFA | SACR-020-SPH-AH-T-0045 | 2022-03-09 | SACR-306-CWS-MA-DWG-0117-04-05 | 2022-03-29 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0101 | 2020-06-02 | 1399/03/13 | SACR-306-CWS-MA-DWG-0117-00-04 | 2020-06-10 | CO | SACR-306-CWS-MA-DWG-0117-00-05 | 2020-09-01 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0169 | 2020-09-02 | 1399/06/12 | SACR-306-CWS-MA-DWG-0117-01-05 | 2020-09-08 | CO | SACR-306-CWS-MA-DWG-0117-01-07 | 2020-09-15 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0174 | 2020-09-15 | 1399/06/25 | SACR-306-CWS-MA-DWG-0117-02-05 | 2020-09-21 | CO | SACR-306-CWS-MA-DWG-0117-02-06 | 2020-10-27 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0203 | 2020-10-27 | 1399/08/06 | SACR-306-CWS-MA-DWG-0117-03-06 | 2020-11-14 | AP | [6 empty] | 04 | IFA | SACR-020-SPH-AH-T-0045 | 2022-03-09 | 1400/12/18 | SACR-306-CWS-MA-DWG-0117-04-05 | 2022-03-29 | AP
30 | ADSH-P-PO-GE-020 | SPH | MA | DWG | 1 | SACR-306-CWS-MA-DWG-0119 |  |  | Detail drawing Of Splash / Film Type packing | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0181 | 2020-09-30 | SACR-306-CWS-MA-DWG-0119-02-04 | 2020-10-04 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0099 | 2020-05-27 | 1399/03/07 | SACR-306-CWS-MA-DWG-0119-00-04 | 2020-06-10 | CO | SACR-306-CWS-MA-DWG-0119-00-05 | 2020-09-06 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0171 | 2020-09-06 | 1399/06/16 | SACR-306-CWS-MA-DWG-0119-01-04 | 2020-09-07 | RJ | SACR-306-CWS-MA-DWG-0119-01-05 | 2020-09-15 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0175 | 2020-09-15 | 1399/06/25 | SACR-306-CWS-MA-DWG-0119-01-10 | 2020-09-21 | APN | SACR-306-CWS-MA-DWG-0119-01-11 | 2020-09-30 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0181 | 2020-09-30 | 1399/07/09 | SACR-306-CWS-MA-DWG-0119-02-04 | 2020-10-04 | AP
31 | ADSH-P-PO-GE-020 | SPH | MA | DWG | 1 | SACR-306-CWS-MA-DWG-0129 |  |  | Detail drawing for Drive shaft | 0 | - |  | 07 | FIN | SACR-020-SPH-AH-T-0040 | 2021-11-01 | SACR-306-CWS-MA-DWG-0129-07-05 | 2021-11-07 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0093 | 2020-05-23 | 1399/03/03 | SACR-306-CWS-MA-DWG-0129-00-04 | 2020-05-30 | CO | SACR-306-CWS-MA-DWG-0129-00-05 | 2020-06-15 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0107 | 2020-06-15 | 1399/03/26 | SACR-306-CWS-MA-DWG-0129-01-04 | 2020-06-21 | RJ | SACR-306-CWS-MA-DWG-0129-01-05 | 2020-06-21 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0110 | 2020-06-21 | 1399/04/01 | SACR-306-CWS-MA-DWG-0129-01-12 | 2020-07-11 | AP | [6 empty] | 02 | FIN | SACR-020-SPH-AH-T-0028 | 2021-05-10 | 1400/02/20 | SACR-306-CWS-MA-DWG-0129-02-09 | 2021-05-22 | CO | SACR-306-CWS-MA-DWG-0129-02-10 | 2021-05-24 | Noted |  |  |  | 03 | FIN | SACR-020-SPH-AH-T-0032 | 2021-05-24 | 1400/03/03 | SACR-306-CWS-MA-DWG-0129-03-07 | 2021-06-02 | CO | SACR-306-CWS-MA-DWG-0129-03-08 | 2021-06-09 | Noted |  |  |  | 04 | IFA | SACR-020-SPH-AH-T-0034 | 2021-06-09 | 1400/03/19 | SACR-306-CWS-MA-DWG-0129-04-04 | 2021-06-16 | APN | SACR-306-CWS-MA-DWG-0129-04-05 | 2021-06-16 | Noted |  |  |  | 05 | FIN | SACR-020-SPH-AH-T-0035 | 2021-06-16 | 1400/03/26 | SACR-306-CWS-MA-DWG-0129-05-04 | 2021-06-16 | AP | [6 empty] | 06 | FIN | SACR-020-SPH-AH-T-0036 | 2021-06-29 | 1400/04/08 | SACR-306-CWS-MA-DWG-0129-06-06 | 2021-07-25 | AP | [6 empty] | 07 | FIN | SACR-020-SPH-AH-T-0040 | 2021-11-01 | 1400/08/10 | SACR-306-CWS-MA-DWG-0129-07-05 | 2021-11-07 | AP
32 | ADSH-P-PO-GE-020 | SPH | MA | DWG | 1 | SACR-306-CWS-MA-DWG-0130 |  |  | 3D Model PDMS File | 0 | - |  | 10 | FIN | SACR-020-SPH-AH-T-0038 | 2021-07-25 | SACR-306-CWS-MA-DWG-0130-10-06 | 2021-07-31 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0139 | 2020-08-09 | 1399/05/19 | SACR-306-CWS-MA-DWG-0130-00-07 | 2020-08-11 | RJ | SACR-306-CWS-MA-DWG-0130-00-08 | 2020-08-11 | Noted |  |  |  | 00 | IFA | SACR-020-1491-AH-T-0149 | 2020-08-11 | 1399/05/21 | SACR-306-CWS-MA-DWG-0130-00-15 | 2020-08-16 | CO | SACR-306-CWS-MA-DWG-0130-00-16 | 2020-09-05 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0170 | 2020-09-05 | 1399/06/15 | SACR-306-CWS-MA-DWG-0130-01-06 | 2020-09-08 | CO | SACR-306-CWS-MA-DWG-0130-01-07 | 2020-10-10 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0194 | 2020-10-10 | 1399/07/19 | SACR-306-CWS-MA-DWG-0130-02-08 | 2020-10-14 | CO | SACR-306-CWS-MA-DWG-0130-02-09 | 2020-11-25 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0215 | 2020-11-25 | 1399/09/05 | SACR-306-CWS-MA-DWG-0130-03-09 | 2020-12-07 | CO | SACR-306-CWS-MA-DWG-0130-03-10 | 2020-12-13 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0233 | 2020-12-13 | 1399/09/23 | SACR-306-CWS-MA-DWG-0130-04-17 | 2021-01-10 | CO | SACR-306-CWS-MA-DWG-0130-04-18 | 2021-02-06 | Noted |  |  |  | 05 | FIN | SACR-020-1491-AH-T-0287 | 2021-02-06 | 1399/11/18 | SACR-306-CWS-MA-DWG-0130-05-07 | 2021-02-13 | APN | SACR-306-CWS-MA-DWG-0130-05-08 | 2021-03-15 | Noted |  |  |  | 06 | FIN | SACR-020-SPH-AH-T-0007 | 2021-03-15 | 1399/12/25 | SACR-306-CWS-MA-DWG-0130-06-10 | 2021-03-31 | CO | SACR-306-CWS-MA-DWG-0130-06-11 | 2021-05-02 | Noted |  |  |  | 07 | IFA | SACR-020-SPH-AH-T-0022 | 2021-05-02 | 1400/02/12 | SACR-306-CWS-MA-DWG-0130-07-06 | 2021-05-08 | CO | SACR-306-CWS-MA-DWG-0130-07-07 | 2021-05-08 | Noted |  |  |  | 08 | IFA | SACR-020-SPH-AH-T-0025 | 2021-05-08 | 1400/02/18 | SACR-306-CWS-MA-DWG-0130-08-14 | 2021-05-22 | APN | SACR-306-CWS-MA-DWG-0130-08-15 | 2021-06-01 | Noted |  |  |  | 09 | FIN | SACR-020-SPH-AH-T-0033 | 2021-06-01 | 1400/03/11 | SACR-306-CWS-MA-DWG-0130-09-08 | 2021-06-14 | CO | SACR-306-CWS-MA-DWG-0130-09-09 | 2021-07-25 | Noted |  |  |  | 10 | FIN | SACR-020-SPH-AH-T-0038 | 2021-07-25 | 1400/05/03 | SACR-306-CWS-MA-DWG-0130-10-06 | 2021-07-31 | AP
33 | ADSH-P-PO-GE-020 | SPH | MA | DWG | 1 | SACR-306-CWS-MA-DWG-0131 |  |  | 3D Model Review Report. | 0 | - |  | 02 | IFA | SACR-020-SPH-AH-T-0023 | 2021-05-02 | SACR-306-CWS-MA-DWG-0131-02-06 | 2021-05-08 | CO | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0199 | 2020-10-21 | 1399/07/30 | SACR-306-CWS-MA-DWG-0131-00-07 | 2020-11-10 | CO | SACR-306-CWS-MA-DWG-0131-00-08 | 2020-12-13 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0234 | 2020-12-13 | 1399/09/23 | SACR-306-CWS-MA-DWG-0131-01-12 | 2020-12-28 | CO | SACR-306-CWS-MA-DWG-0131-01-14 | 2021-05-02 | Noted |  |  |  | 02 | IFA | SACR-020-SPH-AH-T-0023 | 2021-05-02 | 1400/02/12 | SACR-306-CWS-MA-DWG-0131-02-06 | 2021-05-08 | CO
34 | ADSH-P-PO-GE-020 | SPH | MA | DWG | 1 | SACR-306-CWS-MA-DWG-0135 |  |  | General arrangement drawing for cooling tower and basin, | 0 | - |  | 18 | FIN | SACR-020-SPH-AH-T-0037 | 2021-07-25 | SACR-306-CWS-MA-DWG-0135-18-09 | 2021-08-11 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0034 | 2020-03-09 | 1398/12/19 | SACR-306-CWS-MA-DWG-0135-00-12 | 2020-03-15 | CO | SACR-306-CWS-MA-DWG-0135-00-13 | 2020-03-31 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0049 | 2020-04-01 | 1399/01/13 | SACR-306-CWS-MA-DWG-0135-01-04 | 2020-04-04 | RJ | SACR-306-CWS-MA-DWG-0135-01-05 | 2020-04-24 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0067 | 2020-04-24 | 1399/02/05 | SACR-306-CWS-MA-DWG-0135-01-16 | 2020-05-02 | CO | SACR-306-CWS-MA-DWG-0135-01-17 | 2020-05-23 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0096 | 2020-05-23 | 1399/03/03 | SACR-306-CWS-MA-DWG-0135-02-20 | 2020-06-14 | CO | SACR-306-CWS-MA-DWG-0135-02-28 | 2020-07-26 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0132 | 2020-07-26 | 1399/05/05 | SACR-306-CWS-MA-DWG-0135-03-07 | 2020-08-05 | CO | SACR-306-CWS-MA-DWG-0135-03-08 | 2020-08-19 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0156 | 2020-08-19 | 1399/05/29 | SACR-306-CWS-MA-DWG-0135-04-04 | 2020-08-24 | CO | SACR-306-CWS-MA-DWG-0135-04-05 | 2020-08-24 | Noted |  |  |  | 05 | IFA | SACR-020-1491-AH-T-0159 | 2020-08-24 | 1399/06/03 | SACR-306-CWS-MA-DWG-0135-05-14 | 2020-09-08 | CO | SACR-306-CWS-MA-DWG-0135-05-15 | 2020-09-19 | Noted |  |  |  | 06 | IFA | SACR-020-1491-AH-T-0177 | 2020-09-19 | 1399/06/29 | SACR-306-CWS-MA-DWG-0135-06-11 | 2020-09-30 | CO | SACR-306-CWS-MA-DWG-0135-06-12 | 2020-10-05 | Noted |  |  |  | 07 | IFA | SACR-020-1491-AH-T-0191 | 2020-10-05 | 1399/07/14 | SACR-306-CWS-MA-DWG-0135-07-09 | 2020-10-14 | CO | SACR-306-CWS-MA-DWG-0135-07-10 | 2020-10-27 | Noted |  |  |  | 08 | IFA | SACR-020-1491-AH-T-0200 | 2020-10-27 | 1399/08/06 | SACR-306-CWS-MA-DWG-0135-08-10 | 2020-11-04 | APN | SACR-306-CWS-MA-DWG-0135-08-11 | 2020-11-07 | Noted |  |  |  | 09 | IFA | SACR-020-1491-AH-T-0207 | 2020-11-07 | 1399/08/17 | SACR-306-CWS-MA-DWG-0135-09-07 | 2020-11-14 | AP | [6 empty] | 10 | IFA | SACR-020-1491-AH-T-0245 | 2020-12-23 | 1399/10/03 | SACR-306-CWS-MA-DWG-0135-10-10 | 2021-01-02 | CO | SACR-306-CWS-MA-DWG-0135-10-11 | 2021-01-05 | Noted |  |  |  | 11 | IFA | SACR-020-1491-AH-T-0253 | 2021-01-05 | 1399/10/16 | SACR-306-CWS-MA-DWG-0135-11-09 | 2021-01-16 | CO | SACR-306-CWS-MA-DWG-0135-11-10 | 2021-01-30 | Noted |  |  |  | 12 | IFA | SACR-020-1491-AH-T-0277 | 2021-01-30 | 1399/11/11 | SACR-306-CWS-MA-DWG-0135-12-10 | 2021-02-13 | CO | SACR-306-CWS-MA-DWG-0135-12-13 | 2021-03-09 | Noted |  |  |  | 13 | IFA | SACR-020-SPH-AH-T-0004 | 2021-03-09 | 1399/12/19 | SACR-306-CWS-MA-DWG-0135-13-10 | 2021-03-16 | CO | SACR-306-CWS-MA-DWG-0135-13-13 | 2021-04-10 | Noted |  |  |  | 14 | IFA | SACR-020-SPH-AH-T-0013 | 2021-04-10 | 1400/01/21 | SACR-306-CWS-MA-DWG-0135-14-16 | 2021-04-26 | APN | SACR-306-CWS-MA-DWG-0135-14-17 | 2021-04-27 | Noted |  |  |  | 15 | IFA | SACR-020-SPH-AH-T-0018 | 2021-04-27 | 1400/02/07 | SACR-306-CWS-MA-DWG-0135-15-09 | 2021-05-05 | AP | [6 empty] | 16 | IFA | SACR-020-SPH-AH-T-0024 | 2021-05-08 | 1400/02/18 | SACR-306-CWS-MA-DWG-0135-16-09 | 2021-05-15 | CO | SACR-306-CWS-MA-DWG-0135-16-10 | 2021-05-23 | Noted |  |  |  | 17 | IFA | SACR-020-SPH-AH-T-0030 | 2021-05-23 | 1400/03/02 | SACR-306-CWS-MA-DWG-0135-17-09 | 2021-05-30 | AP | [6 empty] | 18 | FIN | SACR-020-SPH-AH-T-0037 | 2021-07-25 | 1400/05/03 | SACR-306-CWS-MA-DWG-0135-18-09 | 2021-08-11 | AP
35 | ADSH-P-PO-GE-020 | SPH | MA | DWG | 1 | SACR-306-CWS-MA-DWG-0137 |  |  | Gear Box drawing details | 0 | - |  | 00 | IFA | SACR-020-SPH-AH-T-0047 | 2022-03-16 | SACR-306-CWS-MA-DWG-0137-00-03 | 2022-03-27 | AP | [8 empty] | 00 | IFA | SACR-020-SPH-AH-T-0047 | 2022-03-16 | 1400/12/25 | SACR-306-CWS-MA-DWG-0137-00-03 | 2022-03-27 | AP
36 | ADSH-P-PO-GE-020 | SPH | MA | LST | 1 | SACR-306-CWS-MA-LST-0063 |  |  | List of component to be erected/installed on site for cooling tower | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0269 | 2021-01-23 | SACR-306-CWS-MA-LST-0063-02-04 | 2021-02-02 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0229 | 2020-12-09 | 1399/09/19 | SACR-306-CWS-MA-LST-0063-00-05 | 2020-12-16 | CO | SACR-306-CWS-MA-LST-0063-00-06 | 2020-12-22 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0243 | 2020-12-22 | 1399/10/02 | SACR-306-CWS-MA-LST-0063-01-04 | 2021-01-02 | CO | SACR-306-CWS-MA-LST-0063-01-05 | 2021-01-23 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0269 | 2021-01-23 | 1399/11/04 | SACR-306-CWS-MA-LST-0063-02-04 | 2021-02-02 | AP
37 | ADSH-P-PO-GE-020 | SPH | MA | LST | 1 | SACR-306-CWS-MA-LST-0064 |  |  | List of operation to be implemented on site for cooling tower | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0285 | 2021-02-03 | SACR-306-CWS-MA-LST-0064-02-04 | 2021-02-13 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0230 | 2020-12-09 | 1399/09/19 | SACR-306-CWS-MA-LST-0064-00-05 | 2020-12-16 | RJ | SACR-306-CWS-MA-LST-0064-00-06 | 2020-12-23 | Noted |  |  |  | 00 | IFA | SACR-020-1491-AH-T-0244 | 2020-12-23 | 1399/10/03 | SACR-306-CWS-MA-LST-0064-00-10 | 2021-01-02 | CO | SACR-306-CWS-MA-LST-0064-00-11 | 2021-01-23 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0270 | 2021-01-23 | 1399/11/04 | SACR-306-CWS-MA-LST-0064-01-07 | 2021-02-03 | APN | SACR-306-CWS-MA-LST-0064-01-08 | 2021-02-03 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0285 | 2021-02-03 | 1399/11/15 | SACR-306-CWS-MA-LST-0064-02-04 | 2021-02-13 | AP
38 | ADSH-P-PO-GE-020 | SPH | MA | LST | 1 | SACR-306-CWS-MA-LST-0065 |  |  | List of verifications and tests to be performed on site for cooling tower | 0 | - |  | 02 | IFA | SACR-020-SPH-AH-T-0029 | 2021-05-11 | SACR-306-CWS-MA-LST-0065-02-09 | 2021-05-22 | APN | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0228 | 2020-12-09 | 1399/09/19 | SACR-306-CWS-MA-LST-0065-00-05 | 2020-12-16 | RJ | SACR-306-CWS-MA-LST-0065-00-06 | 2021-01-27 | Noted |  |  |  | 00 | IFA | SACR-020-1491-AH-T-0274 | 2021-01-27 | 1399/11/08 | SACR-306-CWS-MA-LST-0065-00-14 | 2021-02-14 | CO | SACR-306-CWS-MA-LST-0065-00-15 | 2021-02-28 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0305 | 2021-02-28 | 1399/12/10 | SACR-306-CWS-MA-LST-0065-01-11 | 2021-03-10 | CO | SACR-306-CWS-MA-LST-0065-01-13 | 2021-05-11 | Noted |  |  |  | 02 | IFA | SACR-020-SPH-AH-T-0029 | 2021-05-11 | 1400/02/21 | SACR-306-CWS-MA-LST-0065-02-09 | 2021-05-22 | APN
39 | ADSH-P-PO-GE-020 | SPH | PI | DSH | 1 | SACR-306-CWS-PI-DSH-0030 |  |  | Valve list and data sheet | 0 | - |  | 05 | IFA | SACR-020-1491-AH-T-0238 | 2020-12-15 | SACR-306-CWS-PI-DSH-0030-05-05 | 2020-12-27 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0086 | 2020-05-16 | 1399/02/27 | SACR-306-CWS-PI-DSH-0030-00-10 | 2020-06-09 | CO | SACR-306-CWS-PI-DSH-0030-00-11 | 2020-08-09 | Noted |  |  |  | 01 | FIN | SACR-020-1491-AH-T-0140 | 2020-08-09 | 1399/05/19 | SACR-306-CWS-PI-DSH-0030-01-06 | 2020-08-15 | CO | SACR-306-CWS-PI-DSH-0030-01-07 | 2020-08-31 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0164 | 2020-08-31 | 1399/06/10 | SACR-306-CWS-PI-DSH-0030-02-06 | 2020-09-05 | CO | SACR-306-CWS-PI-DSH-0030-02-07 | 2020-10-10 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0195 | 2020-10-10 | 1399/07/19 | SACR-306-CWS-PI-DSH-0030-03-06 | 2020-10-12 | APN | SACR-306-CWS-PI-DSH-0030-03-07 | 2020-11-29 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0219 | 2020-11-29 | 1399/09/09 | SACR-306-CWS-PI-DSH-0030-04-07 | 2020-12-14 | CO | SACR-306-CWS-PI-DSH-0030-04-08 | 2020-12-15 | Noted |  |  |  | 05 | IFA | SACR-020-1491-AH-T-0238 | 2020-12-15 | 1399/09/25 | SACR-306-CWS-PI-DSH-0030-05-05 | 2020-12-27 | AP
40 | ADSH-P-PO-GE-020 | SPH | PI | LST | 1 | SACR-306-CWS-PI-LST-0027 |  |  | Tie-in point list | 0 | - |  | 04 | FIN | SACR-020-SPH-AH-T-0044 | 2022-01-22 | SACR-306-CWS-PI-LST-0027-04-25 | 2022-02-19 | RJ | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0232 | 2020-12-13 | 1399/09/23 | SACR-306-CWS-PI-LST-0027-00-04 | 2020-12-16 | RJ | SACR-306-CWS-PI-LST-0027-00-05 | 2020-12-26 | Replied | SACR-306-CWS-PI-LST-0027-00-11 | 2021-01-02 | CO | 00 | IFA | SACR-020-1491-AH-T-0265 | 2021-01-18 | 1399/10/29 | SACR-306-CWS-PI-LST-0027-00-18 | 2021-01-23 | CO | SACR-306-CWS-PI-LST-0027-00-19 | 2021-02-03 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0286 | 2021-02-03 | 1399/11/15 | SACR-306-CWS-PI-LST-0027-01-08 | 2021-02-16 | CO | SACR-306-CWS-PI-LST-0027-01-09 | 2021-03-15 | Noted |  |  |  | 02 | IFA | SACR-020-SPH-AH-T-0008 | 2021-03-15 | 1399/12/25 | SACR-306-CWS-PI-LST-0027-02-09 | 2021-03-31 | CO | SACR-306-CWS-PI-LST-0027-02-10 | 2021-05-09 | Noted |  |  |  | 03 | IFA | SACR-020-SPH-AH-T-0026 | 2021-05-09 | 1400/02/19 | SACR-306-CWS-PI-LST-0027-03-07 | 2021-05-22 | APN | SACR-306-CWS-PI-LST-0027-03-08 | 2021-06-07 | Replied | SACR-306-CWS-PI-LST-0027-03-14 | 2021-06-16 | CO | 04 | FIN | SACR-020-SPH-AH-T-0039 | 2021-10-16 | 1400/07/24 | SACR-306-CWS-PI-LST-0027-04-10 | 2021-12-08 | RJ | SACR-306-CWS-PI-LST-0027-04-11 | 2021-12-11 | Noted |  |  |  | 04 | FIN | SACR-020-SPH-AH-T-0042 | 2021-12-12 | 1400/09/21 | SACR-306-CWS-PI-LST-0027-04-18 | 2022-01-18 | RJ | SACR-306-CWS-PI-LST-0027-04-19 | 2022-01-22 | Noted |  |  |  | 04 | FIN | SACR-020-SPH-AH-T-0044 | 2022-01-22 | 1400/11/02 | SACR-306-CWS-PI-LST-0027-04-25 | 2022-02-19 | RJ
41 | ADSH-P-PO-GE-020 | SPH | PI | LST | 1 | SACR-306-CWS-PI-LST-0028 |  |  | Piping line list | 0 | - |  | 07 | IFA | SACR-020-1491-AH-T-0231 | 2020-12-12 | SACR-306-CWS-PI-LST-0028-07-05 | 2020-12-13 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0085 | 2020-05-16 | 1399/02/27 | SACR-306-CWS-PI-LST-0028-00-15 | 2020-06-09 | CO | SACR-306-CWS-PI-LST-0028-00-16 | 2020-06-27 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0111 | 2020-06-27 | 1399/04/07 | SACR-306-CWS-PI-LST-0028-01-07 | 2020-07-11 | CO | SACR-306-CWS-PI-LST-0028-01-08 | 2020-08-01 | Noted |  |  |  | 02 | FIN | SACR-020-1491-AH-T-0134 | 2020-08-01 | 1399/05/11 | SACR-306-CWS-PI-LST-0028-02-06 | 2020-08-11 | CO | SACR-306-CWS-PI-LST-0028-02-07 | 2020-08-28 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0163 | 2020-08-28 | 1399/06/07 | SACR-306-CWS-PI-LST-0028-03-07 | 2020-09-07 | CO | SACR-306-CWS-PI-LST-0028-03-10 | 2020-10-04 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0188 | 2020-10-04 | 1399/07/13 | SACR-306-CWS-PI-LST-0028-04-07 | 2020-10-11 | CO | SACR-306-CWS-PI-LST-0028-04-08 | 2020-11-24 | Noted |  |  |  | 05 | IFA | SACR-020-1491-AH-T-0214 | 2020-11-24 | 1399/09/04 | SACR-306-CWS-PI-LST-0028-05-06 | 2020-11-30 | APN | SACR-306-CWS-PI-LST-0028-05-07 | 2020-12-05 | Noted |  |  |  | 06 | IFA | SACR-020-1491-AH-T-0221 | 2020-12-05 | 1399/09/15 | SACR-306-CWS-PI-LST-0028-06-06 | 2020-12-07 | APN | SACR-306-CWS-PI-LST-0028-06-07 | 2020-12-12 | Noted |  |  |  | 07 | IFA | SACR-020-1491-AH-T-0231 | 2020-12-12 | 1399/09/22 | SACR-306-CWS-PI-LST-0028-07-05 | 2020-12-13 | AP
42 | ADSH-P-PO-GE-020 | SPH | PI | LST | 1 | SACR-306-CWS-PI-LST-0069 |  |  | Surface preparation and painting procedure for cooling tower | 0 | - |  | 04 | IFA | SACR-020-1491-AH-T-0252 | 2021-01-03 | SACR-306-CWS-PI-LST-0069-04-14 | 2021-01-13 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0112 | 2020-07-06 | 1399/04/16 | SACR-306-CWS-PI-LST-0069-00-06 | 2020-07-13 | CO | SACR-306-CWS-PI-LST-0069-00-07 | 2020-07-15 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0117 | 2020-07-15 | 1399/04/25 | SACR-306-CWS-PI-LST-0069-01-08 | 2020-08-04 | RJ | SACR-306-CWS-PI-LST-0069-01-09 | 2020-12-08 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0226 | 2020-12-08 | 1399/09/18 | SACR-306-CWS-PI-LST-0069-01-15 | 2020-12-14 | CO | SACR-306-CWS-PI-LST-0069-01-16 | 2020-12-14 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0236 | 2020-12-14 | 1399/09/24 | SACR-306-CWS-PI-LST-0069-02-06 | 2020-12-16 | APN | SACR-306-CWS-PI-LST-0069-02-07 | 2020-12-27 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0247 | 2020-12-27 | 1399/10/07 | SACR-306-CWS-PI-LST-0069-03-09 | 2021-01-02 | CO | SACR-306-CWS-PI-LST-0069-03-10 | 2021-01-03 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0252 | 2021-01-03 | 1399/10/14 | SACR-306-CWS-PI-LST-0069-04-14 | 2021-01-13 | AP
43 | ADSH-P-PO-GE-020 | SPH | PR | DBA | 1 | SACR-306-CWS-PR-DBA-0014 |  |  | Process description FOR COOLING WATER SYSTEM | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0186 | 2020-10-03 | SACR-306-CWS-PR-DBA-0014-02-05 | 2020-10-06 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0167 | 2020-09-01 | 1399/06/11 | SACR-306-CWS-PR-DBA-0014-00-07 | 2020-09-12 | CO | SACR-306-CWS-PR-DBA-0014-00-08 | 2020-09-19 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0176 | 2020-09-19 | 1399/06/29 | SACR-306-CWS-PR-DBA-0014-01-06 | 2020-09-27 | APN | SACR-306-CWS-PR-DBA-0014-01-07 | 2020-10-03 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0186 | 2020-10-03 | 1399/07/12 | SACR-306-CWS-PR-DBA-0014-02-05 | 2020-10-06 | AP
44 | ADSH-P-PO-GE-020 | SPH | PR | DIA | 1 | SACR-306-CWS-PR-DIA-0017 |  |  | Material Flow Diagram | 0 | - | 738780
45 | ADSH-P-PO-GE-020 | SPH | PR | DIA | 1 | SACR-306-CWS-PR-DIA-0018 |  |  | Cause and Effect Diagram | 0 | - |  | 03 | IFA | SACR-020-SPH-AH-T-0027 | 2021-05-09 | SACR-306-CWS-PR-DIA-0018-03-08 | 2021-05-15 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0263 | 2021-01-16 | 1399/10/27 | SACR-306-CWS-PR-DIA-0018-00-09 | 2021-01-26 | CO | SACR-306-CWS-PR-DIA-0018-00-10 | 2021-02-06 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0288 | 2021-02-06 | 1399/11/18 | SACR-306-CWS-PR-DIA-0018-01-08 | 2021-02-15 | CO | SACR-306-CWS-PR-DIA-0018-01-09 | 2021-02-20 | Replied | SACR-306-CWS-PR-DIA-0018-01-14 | 2021-02-21 | APN | 02 | IFA | SACR-020-SPH-AH-T-0010 | 2021-03-16 | 1399/12/26 | SACR-306-CWS-PR-DIA-0018-02-08 | 2021-03-30 | CO | SACR-306-CWS-PR-DIA-0018-02-09 | 2021-05-09 | Noted |  |  |  | 03 | IFA | SACR-020-SPH-AH-T-0027 | 2021-05-09 | 1400/02/19 | SACR-306-CWS-PR-DIA-0018-03-08 | 2021-05-15 | AP
46 | ADSH-P-PO-GE-020 | SPH | PR | DSH | 1 | SACR-306-CWS-PR-DSH-0004 |  |  | Data sheet for Biocide / Antibacterial Injection Package | 0 | - |  | 04 | IFA | SACR-020-1491-AH-T-0178 | 2020-09-21 | SACR-306-CWS-PR-DSH-0004-04-05 | 2020-09-22 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0060 | 2020-04-14 | 1399/01/26 | SACR-306-CWS-PR-DSH-0004-00-06 | 2020-04-25 | CO | SACR-306-CWS-PR-DSH-0004-00-07 | 2020-04-27 | Replied | SACR-306-CWS-PR-DSH-0004-00-11 | 2020-05-02 | CO | 01 | IFA | SACR-020-1491-AH-T-0076 | 2020-05-03 | 1399/02/14 | SACR-306-CWS-PR-DSH-0004-01-10 | 2020-05-19 | CO | SACR-306-CWS-PR-DSH-0004-01-11 | 2020-08-11 | Noted |  |  |  | 02 | FIN | SACR-020-1491-AH-T-0143 | 2020-08-11 | 1399/05/21 | SACR-306-CWS-PR-DSH-0004-02-09 | 2020-08-23 | CO | SACR-306-CWS-PR-DSH-0004-02-10 | 2020-08-31 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0165 | 2020-08-31 | 1399/06/10 | SACR-306-CWS-PR-DSH-0004-03-08 | 2020-09-10 | CO | SACR-306-CWS-PR-DSH-0004-03-09 | 2020-09-21 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0178 | 2020-09-21 | 1399/06/31 | SACR-306-CWS-PR-DSH-0004-04-05 | 2020-09-22 | AP
47 | ADSH-P-PO-GE-020 | SPH | PR | DSH | 1 | SACR-306-CWS-PR-DSH-0005 |  |  | Data sheet for Acid (H2SO4) Injection Package | 0 | - |  | 05 | IFA | SACR-020-1491-AH-T-0184 | 2020-10-03 | SACR-306-CWS-PR-DSH-0005-05-05 | 2020-10-06 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0060 | 2020-04-14 | 1399/01/26 | SACR-306-CWS-PR-DSH-0005-00-06 | 2020-04-25 | CO | SACR-306-CWS-PR-DSH-0005-00-07 | 2020-04-27 | Replied | SACR-306-CWS-PR-DSH-0005-00-12 | 2020-05-02 | CO | 01 | IFA | SACR-020-1491-AH-T-0077 | 2020-05-03 | 1399/02/14 | SACR-306-CWS-PR-DSH-0005-01-09 | 2020-05-19 | CO | SACR-306-CWS-PR-DSH-0005-01-10 | 2020-08-11 | Noted |  |  |  | 02 | FIN | SACR-020-1491-AH-T-0144 | 2020-08-11 | 1399/05/21 | SACR-306-CWS-PR-DSH-0005-02-09 | 2020-08-23 | CO | SACR-306-CWS-PR-DSH-0005-02-10 | 2020-08-31 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0165 | 2020-08-31 | 1399/06/10 | SACR-306-CWS-PR-DSH-0005-03-08 | 2020-09-10 | CO | SACR-306-CWS-PR-DSH-0005-03-09 | 2020-09-21 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0178 | 2020-09-21 | 1399/06/31 | SACR-306-CWS-PR-DSH-0005-04-07 | 2020-09-27 | APN | SACR-306-CWS-PR-DSH-0005-04-08 | 2020-10-03 | Noted |  |  |  | 05 | IFA | SACR-020-1491-AH-T-0184 | 2020-10-03 | 1399/07/12 | SACR-306-CWS-PR-DSH-0005-05-05 | 2020-10-06 | AP
48 | ADSH-P-PO-GE-020 | SPH | PR | DSH | 1 | SACR-306-CWS-PR-DSH-0006 |  |  | Data sheet for Corrosion Inhibitor / Antiscalant Injection Package | 0 | - |  | 05 | IFA | SACR-020-1491-AH-T-0185 | 2020-10-03 | SACR-306-CWS-PR-DSH-0006-05-05 | 2020-10-06 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0060 | 2020-04-14 | 1399/01/26 | SACR-306-CWS-PR-DSH-0006-00-06 | 2020-04-25 | CO | SACR-306-CWS-PR-DSH-0006-00-07 | 2020-04-27 | Replied | SACR-306-CWS-PR-DSH-0006-00-11 | 2020-05-02 | CO | 01 | IFA | SACR-020-1491-AH-T-0078 | 2020-05-03 | 1399/02/14 | SACR-306-CWS-PR-DSH-0006-01-09 | 2020-05-19 | CO | SACR-306-CWS-PR-DSH-0006-01-10 | 2020-08-11 | Noted |  |  |  | 02 | FIN | SACR-020-1491-AH-T-0145 | 2020-08-11 | 1399/05/21 | SACR-306-CWS-PR-DSH-0006-02-10 | 2020-08-23 | CO | SACR-306-CWS-PR-DSH-0006-02-11 | 2020-08-31 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0165 | 2020-08-31 | 1399/06/10 | SACR-306-CWS-PR-DSH-0006-03-08 | 2020-09-10 | CO | SACR-306-CWS-PR-DSH-0006-03-09 | 2020-09-21 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0178 | 2020-09-21 | 1399/06/31 | SACR-306-CWS-PR-DSH-0006-04-07 | 2020-09-27 | APN | SACR-306-CWS-PR-DSH-0006-04-08 | 2020-10-03 | Noted |  |  |  | 05 | IFA | SACR-020-1491-AH-T-0185 | 2020-10-03 | 1399/07/12 | SACR-306-CWS-PR-DSH-0006-05-05 | 2020-10-06 | AP
49 | ADSH-P-PO-GE-020 | SPH | PR | DSH | 1 | SACR-306-CWS-PR-DSH-0007 |  |  | Filter Data Sheet | 0 | - |  | 03 | IFA | SACR-020-1491-AH-T-0183 | 2020-10-03 | SACR-306-CWS-PR-DSH-0007-03-05 | 2020-10-06 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0151 | 2020-08-15 | 1399/05/25 | SACR-306-CWS-PR-DSH-0007-00-09 | 2020-08-25 | CO | SACR-306-CWS-PR-DSH-0007-00-13 | 2020-08-31 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0166 | 2020-08-31 | 1399/06/10 | SACR-306-CWS-PR-DSH-0007-01-07 | 2020-09-08 | CO | SACR-306-CWS-PR-DSH-0007-01-08 | 2020-09-14 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0173 | 2020-09-14 | 1399/06/24 | SACR-306-CWS-PR-DSH-0007-02-07 | 2020-09-21 | APN | SACR-306-CWS-PR-DSH-0007-02-08 | 2020-10-03 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0183 | 2020-10-03 | 1399/07/12 | SACR-306-CWS-PR-DSH-0007-03-05 | 2020-10-06 | AP
50 | ADSH-P-PO-GE-020 | SPH | PR | DSH | 1 | SACR-306-CWS-PR-DSH-0009 |  |  | Data sheet for Dispersant Injection Package | 0 | - |  | 04 | IFA | SACR-020-1491-AH-T-0178 | 2020-09-21 | SACR-306-CWS-PR-DSH-0009-04-07 | 2020-09-27 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0060 | 2020-04-14 | 1399/01/26 | SACR-306-CWS-PR-DSH-0009-00-07 | 2020-04-25 | CO | SACR-306-CWS-PR-DSH-0009-00-08 | 2020-04-27 | Replied | SACR-306-CWS-PR-DSH-0009-00-12 | 2020-05-02 | CO | 01 | IFA | SACR-020-1491-AH-T-0079 | 2020-05-03 | 1399/02/14 | SACR-306-CWS-PR-DSH-0009-01-09 | 2020-05-19 | CO | SACR-306-CWS-PR-DSH-0009-01-10 | 2020-08-11 | Noted |  |  |  | 02 | FIN | SACR-020-1491-AH-T-0146 | 2020-08-11 | 1399/05/21 | SACR-306-CWS-PR-DSH-0009-02-10 | 2020-08-23 | CO | SACR-306-CWS-PR-DSH-0009-02-11 | 2020-08-31 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0165 | 2020-08-31 | 1399/06/10 | SACR-306-CWS-PR-DSH-0009-03-08 | 2020-09-10 | CO | SACR-306-CWS-PR-DSH-0009-03-09 | 2020-09-21 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0178 | 2020-09-21 | 1399/06/31 | SACR-306-CWS-PR-DSH-0009-04-07 | 2020-09-27 | AP
51 | ADSH-P-PO-GE-020 | SPH | PR | LST | 1 | SACR-306-CWS-PR-LST-0015 |  |  | Equipment list FOR COOLING WATER SYSTEM | 0 | - |  | 05 | FIN | SACR-020-1491-AH-T-0297 | 2021-02-15 | SACR-306-CWS-PR-LST-0015-05-07 | 2021-02-24 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0081 | 2020-05-04 | 1399/02/15 | SACR-306-CWS-PR-LST-0015-00-10 | 2020-05-19 | APN | SACR-306-CWS-PR-LST-0015-00-11 | 2020-05-31 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0100 | 2020-05-31 | 1399/03/11 | SACR-306-CWS-PR-LST-0015-01-08 | 2020-06-09 | CO | SACR-306-CWS-PR-LST-0015-01-09 | 2020-06-14 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0106 | 2020-06-14 | 1399/03/25 | SACR-306-CWS-PR-LST-0015-02-07 | 2020-06-24 | APN | SACR-306-CWS-PR-LST-0015-02-09 | 2021-01-06 | Noted |  |  |  | 03 | FIN | SACR-020-1491-AH-T-0256 | 2021-01-06 | 1399/10/17 | SACR-306-CWS-PR-LST-0015-03-06 | 2021-01-16 | RJ | SACR-306-CWS-PR-LST-0015-03-08 | 2021-01-16 | Noted |  |  |  | 03 | FIN | SACR-020-1491-AH-T-0261 | 2021-01-16 | 1399/10/27 | SACR-306-CWS-PR-LST-0015-03-17 | 2021-01-27 | CO | SACR-306-CWS-PR-LST-0015-03-18 | 2021-01-30 | Noted |  |  |  | 04 | FIN | SACR-020-1491-AH-T-0275 | 2021-01-30 | 1399/11/11 | SACR-306-CWS-PR-LST-0015-04-08 | 2021-02-13 | CO | SACR-306-CWS-PR-LST-0015-04-09 | 2021-02-15 | Noted |  |  |  | 05 | FIN | SACR-020-1491-AH-T-0297 | 2021-02-15 | 1399/11/27 | SACR-306-CWS-PR-LST-0015-05-07 | 2021-02-24 | AP
52 | ADSH-P-PO-GE-020 | SPH | PR | LST | 1 | SACR-306-CWS-PR-LST-0016 |  |  | Chemical Consumption list | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0187 | 2020-10-03 | SACR-306-CWS-PR-LST-0016-02-06 | 2020-10-10 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0160 | 2020-08-26 | 1399/06/05 | SACR-306-CWS-PR-LST-0016-00-04 | 2020-08-31 | CO | SACR-306-CWS-PR-LST-0016-00-05 | 2020-09-01 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0168 | 2020-09-01 | 1399/06/11 | SACR-306-CWS-PR-LST-0016-01-07 | 2020-09-12 | CO | SACR-306-CWS-PR-LST-0016-01-08 | 2020-10-03 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0187 | 2020-10-03 | 1399/07/12 | SACR-306-CWS-PR-LST-0016-02-06 | 2020-10-10 | AP
53 | ADSH-P-PO-GE-020 | SPH | PR | LST | 1 | SACR-306-CWS-PR-LST-0062 |  |  | Utility consumption list for cooling tower | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0301 | 2021-02-20 | SACR-306-CWS-PR-LST-0062-02-06 | 2021-02-27 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0250 | 2020-12-28 | 1399/10/08 | SACR-306-CWS-PR-LST-0062-00-07 | 2021-01-05 | CO | SACR-306-CWS-PR-LST-0062-00-08 | 2021-02-07 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0291 | 2021-02-07 | 1399/11/19 | SACR-306-CWS-PR-LST-0062-01-06 | 2021-02-13 | CO | SACR-306-CWS-PR-LST-0062-01-07 | 2021-02-20 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0301 | 2021-02-20 | 1399/12/02 | SACR-306-CWS-PR-LST-0062-02-06 | 2021-02-27 | AP
54 | ADSH-P-PO-GE-020 | SPH | PR | PFD | 1 | SACR-306-CWS-PR-PFD-0012 |  |  | Process flow diagram with heat and material balance FOR COOLING WATER SYSTEM | 0 | - |  | 05 | IFA | SACR-020-1491-AH-T-0118 | 2020-07-15 | SACR-306-CWS-PR-PFD-0012-05-07 | 2020-07-25 | AP | [8 empty] | 00 | IFC | SACR-020-1491-AH-T-0003 | 2019-12-28 | 1398/10/07 | SACR-306-CWS-PR-PFD-0012-00-08 | 2019-12-30 | RJ | SACR-306-CWS-PR-PFD-0012-00-09 | 2020-01-11 | Noted |  |  |  | 00 | IFC | SACR-020-1491-AH-T-0008 | 2020-01-11 | 1398/10/21 | SACR-306-CWS-PR-PFD-0012-00-18 | 2020-01-25 | CO | SACR-306-CWS-PR-PFD-0012-00-19 | 2020-02-10 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0013 | 2020-02-10 | 1398/11/21 | SACR-306-CWS-PR-PFD-0012-01-06 | 2020-02-24 | CO | SACR-306-CWS-PR-PFD-0012-01-07 | 2020-03-02 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0026 | 2020-03-02 | 1398/12/12 | SACR-306-CWS-PR-PFD-0012-02-09 | 2020-03-11 | CO | SACR-306-CWS-PR-PFD-0012-02-10 | 2020-04-27 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0070 | 2020-04-27 | 1399/02/08 | SACR-306-CWS-PR-PFD-0012-03-05 | 2020-05-04 | APN | SACR-306-CWS-PR-PFD-0012-03-06 | 2020-05-07 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0083 | 2020-05-07 | 1399/02/18 | SACR-306-CWS-PR-PFD-0012-04-15 | 2020-06-02 | CO | SACR-306-CWS-PR-PFD-0012-04-16 | 2020-07-15 | Noted |  |  |  | 05 | IFA | SACR-020-1491-AH-T-0118 | 2020-07-15 | 1399/04/25 | SACR-306-CWS-PR-PFD-0012-05-07 | 2020-07-25 | AP
55 | ADSH-P-PO-GE-020 | SPH | PR | PID | 1 | SACR-306-CWS-PR-PID-0011 |  |  | P&ID FOR COOLING WATER SYSTEM | 0 | - |  | 14 | IFA | SACR-020-SPH-AH-T-0019 | 2021-04-28 | SACR-306-CWS-PR-PID-0011-14-11 | 2021-05-08 | AP | [8 empty] | 00 | IFC | SACR-020-1491-AH-T-0002 | 2019-12-28 | 1398/10/07 | SACR-306-CWS-PR-PID-0011-00-07 | 2019-12-30 | RJ | SACR-306-CWS-PR-PID-0011-00 | 2020-01-11 | Noted |  |  |  | 00 | IFC | SACR-020-1491-AH-T-0007 | 2020-01-11 | 1398/10/21 | SACR-306-CWS-PR-PID-0011-00-18 | 2020-01-25 | CO | SACR-306-CWS-PR-PID-0011-00-19 | 2020-02-10 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0014 | 2020-02-10 | 1398/11/21 | SACR-306-CWS-PR-PID-0011-01-10 | 2020-02-23 | CO | SACR-306-CWS-PR-PID-0011-01-11 | 2020-03-02 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0028 | 2020-03-02 | 1398/12/12 | SACR-306-CWS-PR-PID-0011-02-10 | 2020-03-09 | CO | SACR-306-CWS-PR-PID-0011-02-11 | 2020-04-19 | Replied | SACR-306-CWS-PR-PID-0011-02-16 | 2020-04-22 | CO | 03 | IFA | SACR-020-1491-AH-T-0075 | 2020-05-02 | 1399/02/13 | SACR-306-CWS-PR-PID-0011-03-18 | 2020-05-20 | CO | SACR-306-CWS-PR-PID-0011-03-19 | 2020-07-22 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0131 | 2020-07-22 | 1399/05/01 | SACR-306-CWS-PR-PID-0011-04-12 | 2020-08-04 | CO | SACR-306-CWS-PR-PID-0011-04-13 | 2020-08-26 | Noted |  |  |  | 05 | IFA | SACR-020-1491-AH-T-0162 | 2020-08-26 | 1399/06/05 | SACR-306-CWS-PR-PID-0011-05-14 | 2020-09-07 | CO | SACR-306-CWS-PR-PID-0011-05-17 | 2020-09-26 | Noted |  |  |  | 06 | IFA | SACR-020-1491-AH-T-0180 | 2020-09-26 | 1399/07/05 | SACR-306-CWS-PR-PID-0011-06-10 | 2020-09-30 | CO | SACR-306-CWS-PR-PID-0011-06-11 | 2020-10-06 | Noted |  |  |  | 07 | IFA | SACR-020-1491-AH-T-0193 | 2020-10-06 | 1399/07/15 | SACR-306-CWS-PR-PID-0011-07-13 | 2020-10-20 | CO | SACR-306-CWS-PR-PID-0011-07-14 | 2020-10-31 | Noted |  |  |  | 08 | IFA | SACR-020-1491-AH-T-0204 | 2020-10-31 | 1399/08/10 | SACR-306-CWS-PR-PID-0011-08-11 | 2020-11-04 | CO | SACR-306-CWS-PR-PID-0011-08-12 | 2020-11-08 | Noted |  |  |  | 09 | IFA | SACR-020-1491-AH-T-0209 | 2020-11-08 | 1399/08/18 | SACR-306-CWS-PR-PID-0011-09-10 | 2020-11-14 | APN | SACR-306-CWS-PR-PID-0011-09-12 | 2021-01-23 | Noted |  |  |  | 10 | IFA | SACR-020-1491-AH-T-0268 | 2021-01-23 | 1399/11/04 | SACR-306-CWS-PR-PID-0011-10-09 | 2021-01-30 | CO | SACR-306-CWS-PR-PID-0011-10-10 | 2021-02-06 | Noted |  |  |  | 11 | FIN | SACR-020-1491-AH-T-0290 | 2021-02-06 | 1399/11/18 | SACR-306-CWS-PR-PID-0011-11-10 | 2021-02-16 | CO | SACR-306-CWS-PR-PID-0011-11-11 | 2021-03-14 | Noted |  |  |  | 12 | IFA | SACR-020-SPH-AH-T-0005 | 2021-03-14 | 1399/12/24 | SACR-306-CWS-PR-PID-0011-12-13 | 2021-03-31 | CO | SACR-306-CWS-PR-PID-0011-12-14 | 2021-04-17 | Noted |  |  |  | 13 | IFA | SACR-020-SPH-AH-T-0014 | 2021-04-17 | 1400/01/28 | SACR-306-CWS-PR-PID-0011-13-10 | 2021-04-26 | APN | SACR-306-CWS-PR-PID-0011-13-11 | 2021-04-28 | Noted |  |  |  | 14 | IFA | SACR-020-SPH-AH-T-0019 | 2021-04-28 | 1400/02/08 | SACR-306-CWS-PR-PID-0011-14-11 | 2021-05-08 | AP
56 | ADSH-P-PO-GE-020 | SPH | QM | ITP | 1 | SACR-306-CWS-QM-ITP-0062 |  |  | Inspection and test procedure for all equipment and whole unit | 0 | - |  | 07 | IFA | SACR-020-1491-AH-T-0249 | 2020-12-28 | SACR-306-CWS-QM-ITP-0062-07-06 | 2021-01-03 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0072 | 2020-04-29 | 1399/02/10 | SACR-306-CWS-QM-ITP-0062-00-05 | 2020-05-10 | CO | SACR-306-CWS-QM-ITP-0062-00-08 | 2020-09-23 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0179 | 2020-09-23 | 1399/07/02 | SACR-306-CWS-QM-ITP-0062-01-06 | 2020-09-27 | CO | SACR-306-CWS-QM-ITP-0062-01-10 | 2020-09-30 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0182 | 2020-09-30 | 1399/07/09 | SACR-306-CWS-QM-ITP-0062-02-05 | 2020-10-04 | CO | SACR-306-CWS-QM-ITP-0062-02-06 | 2020-11-07 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0206 | 2020-11-07 | 1399/08/17 | SACR-306-CWS-QM-ITP-0062-03-10 | 2020-11-14 | CO | SACR-306-CWS-QM-ITP-0062-03-11 | 2020-11-28 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0217 | 2020-11-28 | 1399/09/08 | SACR-306-CWS-QM-ITP-0062-04-08 | 2020-12-07 | CO | SACR-306-CWS-QM-ITP-0062-04-09 | 2020-12-15 | Noted |  |  |  | 05 | IFA | SACR-020-1491-AH-T-0239 | 2020-12-15 | 1399/09/25 | SACR-306-CWS-QM-ITP-0062-05-07 | 2020-12-21 | APN | SACR-306-CWS-QM-ITP-0062-05-08 | 2020-12-22 | Noted |  |  |  | 06 | IFA | SACR-020-1491-AH-T-0242 | 2020-12-22 | 1399/10/02 | SACR-306-CWS-QM-ITP-0062-06-06 | 2020-12-27 | APN | SACR-306-CWS-QM-ITP-0062-06-07 | 2020-12-28 | Noted |  |  |  | 07 | IFA | SACR-020-1491-AH-T-0249 | 2020-12-28 | 1399/10/08 | SACR-306-CWS-QM-ITP-0062-07-06 | 2021-01-03 | AP
57 | ADSH-P-PO-GE-020 | SPH | QM | LST | 1 | SACR-306-CWS-QM-LST-0085 |  |  | Packing list package | 0 | - |  | 04 | IFA | SACR-020-1491-AH-T-0262 | 2021-01-16 | SACR-306-CWS-QM-LST-0085-04-05 | 2021-01-23 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0222 | 2020-12-07 | 1399/09/17 | SACR-306-CWS-QM-LST-0085-00-07 | 2020-12-16 | CO | SACR-306-CWS-QM-LST-0085-00-08 | 2020-12-19 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0240 | 2020-12-19 | 1399/09/29 | SACR-306-CWS-QM-LST-0085-01-08 | 2020-12-23 | CO | SACR-306-CWS-QM-LST-0085-01-09 | 2020-12-27 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0246 | 2020-12-27 | 1399/10/07 | SACR-306-CWS-QM-LST-0085-02-08 | 2021-01-02 | CO | SACR-306-CWS-QM-LST-0085-02-09 | 2021-01-05 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0254 | 2021-01-05 | 1399/10/16 | SACR-306-CWS-QM-LST-0085-03-08 | 2021-01-13 | CO | SACR-306-CWS-QM-LST-0085-03-09 | 2021-01-16 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0262 | 2021-01-16 | 1399/10/27 | SACR-306-CWS-QM-LST-0085-04-05 | 2021-01-23 | AP
58 | ADSH-P-PO-GE-020 | SPH | QM | PRC | 1 | SACR-306-CWS-QM-PRC-0046 |  |  | Field performance test procedure for cooling tower | 0 | - |  | 00 | IFA | SACR-020-1491-AH-T-0273 | 2021-01-25 | SACR-306-CWS-QM-PRC-0046-00-09 | 2021-02-11 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0273 | 2021-01-25 | 1399/11/06 | SACR-306-CWS-QM-PRC-0046-00-09 | 2021-02-11 | AP
59 | ADSH-P-PO-GE-020 | SPH | QM | PRC | 1 | SACR-306-CWS-QM-PRC-0067 |  |  | Recommendations for protection during transportation & storage and preservation at site | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0299 | 2021-02-15 | SACR-306-CWS-QM-PRC-0067-02-06 | 2021-02-20 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0235 | 2020-12-14 | 1399/09/24 | SACR-306-CWS-QM-PRC-0067-00-08 | 2020-12-26 | CO | SACR-306-CWS-QM-PRC-0067-00-09 | 2021-01-31 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0281 | 2021-01-31 | 1399/11/12 | SACR-306-CWS-QM-PRC-0067-01-05 | 2021-02-13 | APN | SACR-306-CWS-QM-PRC-0067-01-06 | 2021-02-15 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0299 | 2021-02-15 | 1399/11/27 | SACR-306-CWS-QM-PRC-0067-02-06 | 2021-02-20 | AP
60 | ADSH-P-PO-GE-020 | SPH | SA | DSH | 1 | SACR-306-CWS-SA-DSH-0048 |  |  | Noise Data Sheet for for cooling tower | 0 | - |  | 01 | IFA | SACR-020-SPH-AH-T-0049 | 2022-04-25 | SACR-306-CWS-SA-DSH-0048-01-04 | 2022-04-30 | APN | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0235 | 2020-12-14 | 1399/09/24 | SACR-306-CWS-SA-DSH-0048-00-08 | 2020-12-26 | CO | SACR-306-CWS-SA-DSH-0048-00-09 | 2020-12-28 | Replied | SACR-306-CWS-SA-DSH-0048-00-13 | 2021-01-02 | RJ | 00 | IFA | SACR-020-1491-AH-T-0276 | 2021-01-30 | 1399/11/11 | SACR-306-CWS-SA-DSH-0048-00-22 | 2021-02-11 | RJ | SACR-306-CWS-SA-DSH-0048-00-23 | 2022-04-05 | Noted |  |  |  | 00 | IFA | SACR-020-SPH-AH-T-0048 | 2022-04-05 | 1401/01/16 | SACR-306-CWS-SA-DSH-0048-00-27 | 2022-04-16 | APN | SACR-306-CWS-SA-DSH-0048-00-28 | 2022-04-25 | Noted |  |  |  | 01 | IFA | SACR-020-SPH-AH-T-0049 | 2022-04-25 | 1401/02/05 | SACR-306-CWS-SA-DSH-0048-01-04 | 2022-04-30 | APN
61 | ADSH-P-PO-GE-020 | SPH | ST | CSH | 1 | SACR-306-CWS-ST-CSH-0025 |  |  | Calculation Note for Foundation | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0066 | 2020-04-22 | SACR-306-CWS-ST-CSH-0025-02-04 | 2020-04-28 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0033 | 2020-03-09 | 1398/12/19 | SACR-306-CWS-ST-CSH-0025-00-05 | 2020-03-10 | RJ | SACR-306-CWS-ST-CSH-0025-00-06 | 2020-03-10 | Replied | SACR-306-CWS-ST-CSH-0025-00-09 | 2020-03-11 | CO | 00 | IFA | SACR-020-1491-AH-T-0038 | 2020-03-12 | 1398/12/22 | SACR-306-CWS-ST-CSH-0025-00-16 | 2020-03-16 | CO | SACR-306-CWS-ST-CSH-0025-00-17 | 2020-04-04 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0051 | 2020-04-04 | 1399/01/16 | SACR-306-CWS-ST-CSH-0025-01-06 | 2020-04-04 | CO | SACR-306-CWS-ST-CSH-0025-01-07 | 2020-04-22 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0066 | 2020-04-22 | 1399/02/03 | SACR-306-CWS-ST-CSH-0025-02-04 | 2020-04-28 | AP
62 | ADSH-P-PO-GE-020 | SPH | ST | CSH | 1 | SACR-306-CWS-ST-CSH-0134 |  |  | Calculation Note for structure for cooling tower | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0064 | 2020-04-22 | SACR-306-CWS-ST-CSH-0134-02-05 | 2020-04-28 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0036 | 2020-03-11 | 1398/12/21 | SACR-306-CWS-ST-CSH-0134-00-08 | 2020-03-30 | CO | SACR-306-CWS-ST-CSH-0134-00-09 | 2020-04-02 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0050 | 2020-04-02 | 1399/01/14 | SACR-306-CWS-ST-CSH-0134-01-05 | 2020-04-08 | APN | SACR-306-CWS-ST-CSH-0134-01-06 | 2020-04-22 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0064 | 2020-04-22 | 1399/02/03 | SACR-306-CWS-ST-CSH-0134-02-05 | 2020-04-28 | AP
63 | ADSH-P-PO-GE-020 | SPH | ST | DWG | 1 | SACR-306-CWS-ST-DWG-0024 |  |  | Foundation Reinforcement Plan, Section and details ,BBS (Bar Bending Schedule) | 0 | - |  | 02 | IFA | SACR-020-1491-AH-T-0104 | 2020-06-06 | SACR-306-CWS-ST-DWG-0024-02-08 | 2020-06-23 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0082 | 2020-05-04 | 1399/02/15 | SACR-306-CWS-ST-DWG-0024-00-06 | 2020-05-17 | APN | SACR-306-CWS-ST-DWG-0024-00-07 | 2020-05-24 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0097 | 2020-05-24 | 1399/03/04 | SACR-306-CWS-ST-DWG-0024-01-04 | 2020-06-02 | CO | SACR-306-CWS-ST-DWG-0024-01-05 | 2020-06-06 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0104 | 2020-06-06 | 1399/03/17 | SACR-306-CWS-ST-DWG-0024-02-08 | 2020-06-23 | AP
64 | ADSH-P-PO-GE-020 | SPH | ST | DWG | 1 | SACR-306-CWS-ST-DWG-0026 |  |  | Name plate drawing | 0 | - |  | 00 | IFA | SACR-020-SPH-AH-T-0031 | 2021-05-23 | SACR-306-CWS-ST-DWG-0026-00-12 | 2021-05-31 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0218 | 2020-11-28 | 1399/09/08 | SACR-306-CWS-ST-DWG-0026-00-05 | 2020-12-05 | RJ | SACR-306-CWS-ST-DWG-0026-00-06 | 2021-05-23 | Noted |  |  |  | 00 | IFA | SACR-020-SPH-AH-T-0031 | 2021-05-23 | 1400/03/02 | SACR-306-CWS-ST-DWG-0026-00-12 | 2021-05-31 | AP
65 | ADSH-P-PO-GE-020 | SPH | MA | INX | 1 | SACR-306-GEN-MA-INX-0072 |  |  | Vendor Final Book | 0 | - | 738780
66 | ADSH-P-PO-GE-020 | SPH | MA | LST | 1 | SACR-306-GEN-MA-LST-0004 |  |  | Sub-vendor List | 0 | - |  | 01 | IFA | SACR-020-SPH-AH-T-0021 | 2021-05-01 | SACR-306-GEN-MA-LST-0004-01-05 | 2021-05-12 | AP | [8 empty] | 00 | IFA | SACR-020-SPH-AH-T-0001 | 2021-03-03 | 1399/12/13 | SACR-306-GEN-MA-LST-0004-00-11 | 2021-03-31 | CO | SACR-306-GEN-MA-LST-0004-00-12 | 2021-05-01 | Noted |  |  |  | 01 | IFA | SACR-020-SPH-AH-T-0021 | 2021-05-01 | 1400/02/11 | SACR-306-GEN-MA-LST-0004-01-05 | 2021-05-12 | AP
67 | ADSH-P-PO-GE-020 | SPH | MA | LST | 1 | SACR-306-GEN-MA-LST-0010 |  |  | Un-priced copy of main sub-orders | 0 | - |  | 01 | IFA | SACR-020-1491-AH-T-0279 | 2021-01-30 | SACR-306-GEN-MA-LST-0010-01-04 | 2021-02-11 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0248 | 2020-12-27 | 1399/10/07 | SACR-306-GEN-MA-LST-0010-00-05 | 2021-01-19 | APN | SACR-306-GEN-MA-LST-0010-00-06 | 2021-01-30 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0279 | 2021-01-30 | 1399/11/11 | SACR-306-GEN-MA-LST-0010-01-04 | 2021-02-11 | AP
68 | ADSH-P-PO-GE-020 | SPH | MA | LST | 1 | SACR-306-GEN-MA-LST-0064 |  |  | Spare parts and interchangeability record -Erection, Testing, Pre-Commissioning and Commissioning. | 0 | - |  | 03 | FIN | SACR-020-1491-AH-T-0278 | 2021-01-30 | SACR-306-GEN-MA-LST-0064-03-04 | 2021-02-13 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0227 | 2020-12-08 | 1399/09/18 | SACR-306-GEN-MA-LST-0064-00-04 | 2020-12-16 | CO | SACR-306-GEN-MA-LST-0064-00-05 | 2020-12-20 | Noted |  |  |  | 01 | IFI | SACR-020-1491-AH-T-0241 | 2020-12-20 | 1399/09/30 | SACR-306-GEN-MA-LST-0064-01-05 | 2021-01-06 | CO | SACR-306-GEN-MA-LST-0064-01-06 | 2021-01-13 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0260 | 2021-01-13 | 1399/10/24 | SACR-306-GEN-MA-LST-0064-02-04 | 2021-01-27 | APN | SACR-306-GEN-MA-LST-0064-02-05 | 2021-01-30 | Noted |  |  |  | 03 | FIN | SACR-020-1491-AH-T-0278 | 2021-01-30 | 1399/11/11 | SACR-306-GEN-MA-LST-0064-03-04 | 2021-02-13 | AP
69 | ADSH-P-PO-GE-020 | SPH | MA | LST | 1 | SACR-306-GEN-MA-LST-0065 |  |  | Spare parts and interchangeability record - Two(2) years operation | 0 | - |  | 03 | IFA | SACR-020-1491-AH-T-0272 | 2021-01-24 | SACR-306-GEN-MA-LST-0065-03-05 | 2021-02-11 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0224 | 2020-12-07 | 1399/09/17 | SACR-306-GEN-MA-LST-0065-00-04 | 2020-12-08 | RJ | SACR-306-GEN-MA-LST-0065-00-05 | 2020-12-08 | Noted |  |  |  | 00 | IFA | SACR-020-1491-AH-T-0225 | 2020-12-08 | 1399/09/18 | SACR-306-GEN-MA-LST-0065-00-09 | 2020-12-16 | CO | SACR-306-GEN-MA-LST-0065-00-10 | 2020-12-20 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0241 | 2020-12-20 | 1399/09/30 | SACR-306-GEN-MA-LST-0065-01-05 | 2021-01-02 | CO | SACR-306-GEN-MA-LST-0065-01-06 | 2021-01-10 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0259 | 2021-01-10 | 1399/10/21 | SACR-306-GEN-MA-LST-0065-02-04 | 2021-01-13 | APN | SACR-306-GEN-MA-LST-0065-02-05 | 2021-01-24 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0272 | 2021-01-24 | 1399/11/05 | SACR-306-GEN-MA-LST-0065-03-05 | 2021-02-11 | AP
70 | ADSH-P-PO-GE-020 | SPH | MA | LST | 1 | SACR-306-GEN-MA-LST-0066 |  |  | Utility consumption list | 0 | - | 738780
71 | ADSH-P-PO-GE-020 | SPH | MA | LST | 1 | SACR-306-GEN-MA-LST-0071 |  |  | Final book index | 0 | - | 738780
72 | ADSH-P-PO-GE-020 | SPH | PC | LST | 1 | SACR-306-GEN-PC-LST-0001 |  |  | VENDOR DOCUMENTS INDEX & SCHEDULE FOR COOLING WATER SYSTEM | 0 | - |  | 15 | FIN | SACR-020-SPH-AH-T-0020 | 2021-05-01 | SACR-306-GEN-PC-LST-0001-15-06 | 2021-05-08 | AP | [8 empty] | 00 | IFC | SACR-020-1491-AH-T-0001 | 2019-12-28 | 1398/10/07 | SACR-306-GEN-PC-LST-0001-00-10 | 2020-01-05 | RJ | RSH-SACR-306-CWS-PC-LST-0001-00 | 2020-01-13 | Noted |  |  |  | 00 | IFC | SACR-020-1491-AH-T-0009 | 2020-01-13 | 1398/10/23 | SACR-306-GEN-PC-LST-0001-00-18 | 2020-01-14 | RJ | SACR-306-GEN-PC-LST-0001-00-20 | 2020-01-28 | Noted |  |  |  | 00 | IFA | SACR-020-1491-AH-T-0011 | 2020-02-03 | 1398/11/14 | SACR-306-GEN-PC-LST-0001-00-31 | 2020-02-12 | CO | SACR-306-GEN-PC-LST-0001-00-32 | 2020-02-17 | Replied | SACR-306-GEN-PC-LST-0001-00-37 | 2020-02-19 | CO | 01 | IFA | SACR-020-1491-AH-T-0020 | 2020-02-19 | 1398/11/30 | SACR-306-GEN-PC-LST-0001-01-06 | 2020-02-25 | CO | SACR-306-GEN-PC-LST-0001-01-07 | 2020-02-29 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0021 | 2020-02-29 | 1398/12/10 | SACR-306-GEN-PC-LST-0001-02-03 | 2020-02-29 | RJ | SACR-306-GEN-PC-LST-0001-02-05 | 2020-02-29 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0022 | 2020-02-29 | 1398/12/10 | SACR-306-GEN-PC-LST-0001-02-13 | 2020-03-04 | CO | SACR-306-GEN-PC-LST-0001-02-15 | 2020-03-10 | Noted |  |  |  | 03 | IFA | SACR-020-1491-AH-T-0035 | 2020-03-10 | 1398/12/20 | SACR-306-GEN-PC-LST-0001-03-06 | 2020-03-14 | APN | SACR-306-GEN-PC-LST-0001-03-07 | 2020-03-15 | Noted |  |  |  | 04 | IFA | SACR-020-1491-AH-T-0040 | 2020-03-17 | 1398/12/27 | SACR-306-GEN-PC-LST-0001-04-05 | 2020-03-18 | APN | SACR-306-GEN-PC-LST-0001-04-06 | 2020-03-18 | Noted |  |  |  | 05 | IFA | SACR-020-1491-AH-T-0041 | 2020-03-18 | 1398/12/28 | SACR-306-GEN-PC-LST-0001-05-03 | 2020-03-25 | APN | SACR-306-GEN-PC-LST-0001-05-04 | 2020-03-25 | Noted |  |  |  | 06 | IFA | SACR-020-1491-AH-T-0045 | 2020-03-25 | 1399/01/06 | SACR-306-GEN-PC-LST-0001-06-04 | 2020-03-29 | AP | [6 empty] | 07 | IFA | SACR-020-1491-AH-T-0048 | 2020-03-29 | 1399/01/10 | SACR-306-GEN-PC-LST-0001-07-04 | 2020-03-30 | AP | [6 empty] | 08 | FIN | SACR-020-1491-AH-T-0068 | 2020-04-27 | 1399/02/08 | SACR-306-GEN-PC-LST-0001-08-04 | 2020-05-03 | APN | SACR-306-GEN-PC-LST-0001-08-07 | 2020-05-04 | Noted |  |  |  | 09 | IFA | SACR-020-1491-AH-T-0080 | 2020-05-04 | 1399/02/15 | SACR-306-GEN-PC-LST-0001-09-12 | 2020-06-02 | CO | SACR-306-GEN-PC-LST-0001-09-13 | 2020-08-23 | Noted |  |  |  | 10 | IFA | SACR-020-1491-AH-T-0158 | 2020-08-23 | 1399/06/02 | SACR-306-GEN-PC-LST-0001-10-17 | 2020-09-01 | CO | SACR-306-GEN-PC-LST-0001-10-18 | 2020-11-04 | Noted |  |  |  | 11 | IFA | SACR-020-1491-AH-T-0205 | 2020-11-04 | 1399/08/14 | SACR-306-GEN-PC-LST-0001-11-09 | 2020-11-14 | AP | [6 empty] | 12 | FIN | SACR-020-1491-AH-T-0289 | 2021-02-06 | 1399/11/18 | SACR-306-GEN-PC-LST-0001-12-05 | 2021-02-13 | APN | SACR-306-GEN-PC-LST-0001-12-06 | 2021-03-03 | Noted |  |  |  | 13 | FIN | SACR-020-SPH-AH-T-0002 | 2021-03-03 | 1399/12/13 | SACR-306-GEN-PC-LST-0001-13-05 | 2021-03-13 | APN | SACR-306-GEN-PC-LST-0001-13-06 | 2021-03-16 | Noted |  |  |  | 14 | FIN | SACR-020-SPH-AH-T-0009 | 2021-03-16 | 1399/12/26 | SACR-306-GEN-PC-LST-0001-14-05 | 2021-03-27 | APN | SACR-306-GEN-PC-LST-0001-14-06 | 2021-05-01 | Noted |  |  |  | 15 | FIN | SACR-020-SPH-AH-T-0020 | 2021-05-01 | 1400/02/11 | SACR-306-GEN-PC-LST-0001-15-06 | 2021-05-08 | AP
73 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0081 |  |  | MONTHLY PROGRESS REPORT-01 | 0 | - |  | 00 | IFA | SACR-020-1491-AH-T-0061 | 2020-04-16 | SACR-306-GEN-PL-PRC-0081-00-05 | 2020-04-25 | RJ | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0061 | 2020-04-16 | 1399/01/28 | SACR-306-GEN-PL-PRC-0081-00-05 | 2020-04-25 | RJ
74 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0082 |  |  | MONTHLY PROGRESS REPORT-02 | 0 | - |  | 00 | IFA | SACR-020-1491-AH-T-0092 | 2020-05-20 | SACR-306-GEN-PL-PRC-0082-00-07 | 2020-05-30 | RJ | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0092 | 2020-05-20 | 1399/02/31 | SACR-306-GEN-PL-PRC-0082-00-07 | 2020-05-30 | RJ
75 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0083 |  |  | MONTHLY PROGRESS REPORT-03 | 0 | - | 738780
76 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0084 |  |  | MONTHLY PROGRESS REPORT-04 | 0 | - | 738780
77 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0085 |  |  | MONTHLY PROGRESS REPORT-05 | 0 | - | 738780
78 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0086 |  |  | MONTHLY PROGRESS REPORT-06 | 0 | - | 738780
79 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0087 |  |  | MONTHLY PROGRESS REPORT-07 | 0 | - | 738780
80 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0088 |  |  | MONTHLY PROGRESS REPORT-08 | 0 | - | 738780
81 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0089 |  |  | MONTHLY PROGRESS REPORT-09 | 0 | - | 738780
82 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0090 |  |  | MONTHLY PROGRESS REPORT-10 | 0 | - |  | 00 | IFA | SACR-020-1491-AH-T-0298 | 2021-02-15 | SACR-306-GEN-PL-PRC-0090-00-07 | 2021-04-12 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0298 | 2021-02-15 | 1399/11/27 | SACR-306-GEN-PL-PRC-0090-00-07 | 2021-04-12 | AP
83 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0091 |  |  | MONTHLY PROGRESS REPORT-11 | 0 | - |  | 00 | IFA | SACR-020-1491-AH-T-0102 | 2020-06-03 | SACR-306-GEN-PL-PRC-0091-00-08 | 2020-06-27 | RJ | SACR-306-GEN-PL-PRC-0091-00-09 | 2020-07-04 | Replied | SACR-306-GEN-PL-PRC-0091-00-12 | 2020-07-04 | CO |  |  | 00 | IFA | SACR-020-1491-AH-T-0102 | 2020-06-03 | 1399/03/14 | SACR-306-GEN-PL-PRC-0091-00-08 | 2020-06-27 | RJ | SACR-306-GEN-PL-PRC-0091-00-09 | 2020-07-04 | Replied | SACR-306-GEN-PL-PRC-0091-00-12 | 2020-07-04 | CO
84 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0092 |  |  | MONTHLY PROGRESS REPORT-12 | 0 | - |  | 00 | IFA | SACR-020-1491-AH-T-0109 | 2020-06-20 | SACR-306-GEN-PL-PRC-0092-00-07 | 2020-07-06 | CO | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0109 | 2020-06-20 | 1399/03/31 | SACR-306-GEN-PL-PRC-0092-00-07 | 2020-07-06 | CO
85 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0101 |  |  | Biweekly PROGRESS REPORT-01 | 0 | - |  | 00 | IFA | SACR-020-1491-AH-T-0074 | 2020-05-02 | SACR-306-GEN-PL-PRC-0101-00-04 | 2020-05-11 | CO | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0074 | 2020-05-02 | 1399/02/13 | SACR-306-GEN-PL-PRC-0101-00-04 | 2020-05-11 | CO
86 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0102 |  |  | Biweekly PROGRESS REPORT-02 | 0 | - | 738780
87 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0103 |  |  | Biweekly PROGRESS REPORT-03 | 0 | - |  | 00 | IFA | SACR-020-1491-AH-T-0220 | 2020-11-30 | SACR-306-GEN-PL-PRC-0103-00-06 | 2020-12-14 | CO | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0220 | 2020-11-30 | 1399/09/10 | SACR-306-GEN-PL-PRC-0103-00-06 | 2020-12-14 | CO
88 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0104 |  |  | Biweekly PROGRESS REPORT-04 | 0 | - |  | 00 | IFA | SACR-020-1491-AH-T-0255 | 2021-01-05 | SACR-306-GEN-PL-PRC-0104-00-07 | 2021-01-19 | CO | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0255 | 2021-01-05 | 1399/10/16 | SACR-306-GEN-PL-PRC-0104-00-07 | 2021-01-19 | CO
89 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0105 |  |  | Biweekly PROGRESS REPORT-05 | 0 | - |  | 00 | IFA | SACR-020-SPH-AH-T-0011 | 2021-03-18 | SACR-306-GEN-PL-PRC-0105-00-06 | 2021-04-12 | AP | [8 empty] | 00 | IFA | SACR-020-SPH-AH-T-0011 | 2021-03-18 | 1399/12/28 | SACR-306-GEN-PL-PRC-0105-00-06 | 2021-04-12 | AP
90 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0106 |  |  | Biweekly PROGRESS REPORT-06 | 0 | - | 738780
91 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0107 |  |  | Biweekly PROGRESS REPORT-07 | 0 | - | 738780
92 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0108 |  |  | Biweekly PROGRESS REPORT-08 | 0 | - | 738780
93 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0109 |  |  | Biweekly PROGRESS REPORT-09 | 0 | - | 738780
94 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0110 |  |  | Biweekly PROGRESS REPORT-10 | 0 | - | 738780
95 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0111 |  |  | Biweekly PROGRESS REPORT-11 | 0 | - | 738780
96 | ADSH-P-PO-GE-020 | SPH | PL | PRC | 4 | SACR-306-GEN-PL-PRC-0112 |  |  | Biweekly PROGRESS REPORT-12 | 0 | - | 738780
97 | ADSH-P-PO-GE-020 | SPH | PL | SCH | 1 | SACR-306-GEN-PL-SCH-0005 |  |  | Project Time schedule | 0 | - |  | 05 | IFA | SACR-020-1491-AH-T-0213 | 2020-11-22 | SACR-306-GEN-PL-SCH-0005-05-06 | 2020-11-23 | AP | [8 empty] | 00 | IFC | SACR-020-1491-AH-T-0004 | 2019-12-30 | 1398/10/09 | SACR-306-GEN-PL-SCH-0005-00-03 | 2019-12-30 | RJ | SACR-306-GEN-PL-SCH-0005 | 2019-12-30 | Noted |  |  |  | 00 | IFC | SACR-020-1491-AH-T-0005 | 2019-12-30 | 1398/10/09 | SACR-306-GEN-PL-SCH-0005-00-07 | 2020-01-01 | RJ | SACR-306-GEN-PL-SCH-0005-00-08 | 2020-01-04 | Noted |  |  |  | 00 | IFC | SACR-020-1491-AH-T-0006 | 2020-01-04 | 1398/10/14 | SACR-306-GEN-PL-SCH-0005-00-14 | 2020-01-14 | RJ | SACR-306-GEN-PL-SCH-0005-00-15 | 2020-01-28 | Noted |  |  |  | 00 | IFA | SACR-020-1491-AH-T-0012 | 2020-02-03 | 1398/11/14 | SACR-306-GEN-PL-SCH-0005-00-21 | 2020-02-15 | CO | SACR-306-GEN-PL-SCH-0005-00-22 | 2020-03-07 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0032 | 2020-03-07 | 1398/12/17 | SACR-306-GEN-PL-SCH-0005-01-04 | 2020-03-09 | AP | [6 empty] | 02 | IFA | SACR-020-1491-AH-T-0037 | 2020-03-11 | 1398/12/21 | SACR-306-GEN-PL-SCH-0005-02-03 | 2020-03-14 | AP | [6 empty] | 03 | FIN | SACR-020-1491-AH-T-0069 | 2020-04-27 | 1399/02/08 | SACR-306-GEN-PL-SCH-0005-03-04 | 2020-05-04 | CO | SACR-306-GEN-PL-SCH-0005-03-05 | 2020-05-06 | Replied | SACR-306-GEN-PL-SCH-0005-03-08 | 2020-05-10 | CO | 04 | IFA | SACR-020-1491-AH-T-0211 | 2020-11-11 | 1399/08/21 | SACR-306-GEN-PL-SCH-0005-04-06 | 2020-11-17 | CO | SACR-306-GEN-PL-SCH-0005-04-07 | 2020-11-22 | Noted |  |  |  | 05 | IFA | SACR-020-1491-AH-T-0213 | 2020-11-22 | 1399/09/02 | SACR-306-GEN-PL-SCH-0005-05-06 | 2020-11-23 | AP
98 | ADSH-P-PO-GE-020 | SPH | PL | SCH | 1 | SACR-306-GEN-PL-SCH-0008 |  |  | Estimated erection schedule and commissioning schedule including vendor supervision plan for reference | 0 | - |  | 00 | IFA | SACR-020-1491-AH-T-0292 | 2021-02-07 | SACR-306-GEN-PL-SCH-0008-00-05 | 2021-02-20 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0292 | 2021-02-07 | 1399/11/19 | SACR-306-GEN-PL-SCH-0008-00-05 | 2021-02-20 | AP
99 | ADSH-P-PO-GE-020 | SPH | PL | SCH | 1 | SACR-306-GEN-PL-SCH-0009 |  |  | Organization chart | 0 | - |  | 01 | IFA | SACR-020-1491-AH-T-0280 | 2021-01-30 | SACR-306-GEN-PL-SCH-0009-01-05 | 2021-02-01 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0059 | 2020-04-13 | 1399/01/25 | SACR-306-GEN-PL-SCH-0009-00-04 | 2020-04-22 | APN | SACR-306-GEN-PL-SCH-0009-00-05 | 2021-01-30 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0280 | 2021-01-30 | 1399/11/11 | SACR-306-GEN-PL-SCH-0009-01-05 | 2021-02-01 | AP
100 | ADSH-P-PO-GE-020 | SPH | QM | LST | 1 | SACR-306-GEN-QM-LST-0069 |  |  | Packing list | 0 | - | 738780
101 | ADSH-P-PO-GE-020 | SPH | QM | PRC | 1 | SACR-306-GEN-QM-PRC-0067 |  |  | Installation, operation and maintenance manual | 0 | - |  | 05 | FIN | SACR-020-SPH-AH-T-0050 | 2022-05-17 | SACR-306-GEN-QM-PRC-0067-05-09 | 2022-05-31 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0223 | 2020-12-07 | 1399/09/17 | SACR-306-GEN-QM-PRC-0067-00-11 | 2020-12-23 | CO | SACR-306-GEN-QM-PRC-0067-00-12 | 2021-01-09 | Noted |  |  |  | 01 | IFA | SACR-020-1491-AH-T-0258 | 2021-01-09 | 1399/10/20 | SACR-306-GEN-QM-PRC-0067-01-13 | 2021-01-23 | CO | SACR-306-GEN-QM-PRC-0067-01-14 | 2021-02-08 | Noted |  |  |  | 02 | IFA | SACR-020-1491-AH-T-0293 | 2021-02-08 | 1399/11/20 | SACR-306-GEN-QM-PRC-0067-02-09 | 2021-02-20 | CO | SACR-306-GEN-QM-PRC-0067-02-10 | 2021-02-27 | Noted |  |  |  | 03 | FIN | SACR-020-1491-AH-T-0304 | 2021-02-27 | 1399/12/09 | SACR-306-GEN-QM-PRC-0067-03-11 | 2021-03-06 | CO | SACR-306-GEN-QM-PRC-0067-03-12 | 2021-03-17 | Replied | SACR-306-GEN-QM-PRC-0067-03-16 | 2021-03-27 | CO | 04 | FIN | SACR-020-SPH-AH-T-0017 | 2021-04-24 | 1400/02/04 | SACR-306-GEN-QM-PRC-0067-04-16 | 2021-05-10 | APN | SACR-306-GEN-QM-PRC-0067-04-17 | 2022-05-17 | Noted |  |  |  | 05 | FIN | SACR-020-SPH-AH-T-0050 | 2022-05-17 | 1401/02/27 | SACR-306-GEN-QM-PRC-0067-05-09 | 2022-05-31 | AP
102 | ADSH-P-PO-GE-020 | SPH | QM | PRC | 1 | SACR-306-GEN-QM-PRC-0068 |  |  | Pre-commissioning, commissioning procedure and check list | 0 | - |  | 02 | IFA | SACR-020-SPH-AH-T-0006 | 2021-03-15 | SACR-306-GEN-QM-PRC-0068-02-06 | 2021-04-26 | AP | [8 empty] | 00 | IFA | SACR-020-1491-AH-T-0266 | 2021-01-18 | 1399/10/29 | SACR-306-GEN-QM-PRC-0068-00-05 | 2021-01-31 | CO | SACR-306-GEN-QM-PRC-0068-00-06 | 2021-03-07 | Noted |  |  |  | 01 | IFA | SACR-020-SPH-AH-T-0003 | 2021-03-07 | 1399/12/17 | SACR-306-GEN-QM-PRC-0068-01-05 | 2021-03-13 | APN | SACR-306-GEN-QM-PRC-0068-01-06 | 2021-03-15 | Noted |  |  |  | 02 | IFA | SACR-020-SPH-AH-T-0006 | 2021-03-15 | 1399/12/25 | SACR-306-GEN-QM-PRC-0068-02-06 | 2021-04-26 | AP